## All by RM Cat_v3_no Donper->HP (hidden)
[13 empty] | 3642.6838 | 3022.9193 |  | 0 | 0 | 0 | 0 | YTD=YEAR-TO-DATE / YTG=YEAR-TO-GO
[13 empty] | with Sep'24 INITIAL BASELINE VOLUMES |  | DO NOT COPY/PASTE | as per INITIAL BASELINE VOLUMES |  | as per LATEST FULL YEAR (YTD ACTUAL + YTG FORECAST) VOLUMES |  | DO NOT COPY/PASTE IN THESE COLUMNS
[12 empty] | INITIALLY REPORTED |  |  | LATEST ASSESSMENT |  |  | LATEST ASSESSMENT | [7 empty] | % Allocation of Total Benefit
Project Code | Project Name & Brief Description | RM Category | Initiating Department | Plant / Dept | Project Classification | Project Type | PDD Approval Required | PDD Approval Acquired | Customer Approval Required | Customer Approval Acquired | Project Booking | Initial PLAN - Implementation Date (= in Production) | Initial PLAN - Annualized (kEur) PLAN | Initial PLAN - Within 2025 (kEur) | Latest STATUS - Implementation Date (= in Production) | Latest STATUS - Annualized (kEur) | Latest STATUS - Within 2025 (kEur) | Latest STATUS - Annualized (kEur) | Latest STATUS - Within 2025 (kEur) | Procurement Status | General Status | Detailed Status | Remarks | Initiative Success Confidence Level | Result Success Confidence Factor in % | IND | INN | ROM | SAF | Proposed Actions | Initiative Success Numeric Confidence Level
25IND025 | WOT : Zhongshang to BMR (5R/6R/7R) | WOT | Central Procurement | IND | Central | III: Alternative Sourcing (Conditions or Security) | YES | NO | NO | n/a | in BDG | Jan_25 | 6.7399 | 6.7399 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | HI | 90% | 100% | 0% | 0% | 0% |  | 3
25SRC048 | Pallet | Wooden Pallets | Central Sourcing | SRC | Central | III: Alternative Sourcing (Conditions or Security) | 0 | 0 | 0 | 0 | in BDG | Apr_25 | 10.75 | 7.525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50% share | HI | 80% | 0% | 0% | 100% | 0% |  | 3
25SAF011 | Pallet Optimization | Wooden Pallets | R&PD and PRC | SAF | Central | I: Conditions or Specs Negotiation | 0 | 0 | 0 | 0 | in BDG | Apr_25 | 23 | 17.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Study in progress with local Eng/India PD | HI | 80% | 0% | 0% | 0% | 100% | New design for Pallet. Shared drawings with supplier for quoation. | 3
25ROM005 | Validate alternative supplier (new Arco Plast Vs. Rual) | Wooden Pallets | Central Procurement | ROM | Central | III: Alternative Sourcing (Conditions or Security) | 0 | 0 | 0 | 0 | in BDG | Jan_25 | 19.1725 | 19.1725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | H1 share business 40/60 and for H2 share business 60/40 | HI | 90% | 0% | 0% | 100% | 0% | to finalise the validation of Arcoplast; to agree the share of business with SC for implementation | 3
25IND024 | Thermostat : Alternate Supplier Development Robertshaw -> Under evaluation | Thermostats | Central Procurement | IND | Central | III: Alternative Sourcing (Conditions or Security) | YES | NO | NO | n/a | in BDG | Jan_25 | 3.0667 | 3.0667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | MED | 80% | 100% | 0% | 0% | 0% |  | 2
25SRC047 | Tapes | Tapes&Other Packaging Material | Central Sourcing | SRC | Central | III: Alternative Sourcing (Conditions or Security) | 0 | 0 | 0 | 0 | in BDG | Sep_25 | 22.8586 | 4.5717 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50% share - not started | MED | 60% | 0% | 0% | 0% | 0% |  | 2
25CPG006 | Introduce alternative vs. Lampre for PPGI /Timisoara needs | Steel-PPGI | Central Procurement | CPG | Central | II: Sourcing (Supply Extension or Re-Spec'ing) | 0 | 0 | 0 | 0 | in BDG | Feb_25 | 376 | 342 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Share business Lampre, Elastron, Voestalpine (€140 avg landed cost saving per MT / 2700 MT different SOBs per quarter gradually reducing Lampre to 20% and the rest to Elastron & Voestalpine) | HI | 90% | 0% | 0% | 100% | 0% | Trials to complete in Sept/Oct. Share of business for 2025. Improve conditions (Nego with focus on Payment terms /Lead time) | 3
25SAF010 | Prepainted steel from 0.45->0.40mm | Steel-PPGI | Local R&PD | SAF | Local | I: Conditions or Specs Negotiation | 0 | 0 | 0 | 0 | in BDG | Apr_25 | 32 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Price negotiations pending | MED | 50% | 0% | 0% | 0% | 100% | If successful, TF update will be required from PD India | 2
25SAF009 | Sourcing with another local supplier for better pricing | Steel-GI | Central Procurement | SAF | Central | III: Alternative Sourcing (Conditions or Security) | 0 | 0 | 0 | 0 | in BDG | Apr_25 | 18 | 13.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Awaiting Supplier costing, Requirment and confirmed Lead time, 'Support from Production and PD/ENG for sample & FPAP | HI | 90% | 0% | 0% | 0% | 100% | Provide supplier with respective drawings and annual Vol. Awaiting for supplier response & confirmation that they can deliver our requirement while meeting our quality expectations. Verify supplier drawings with Frigoglass(Evidence).Negotiate Pricing and secure savings. Receive samples and perform FPAP and upon approval receive pilot order | 3
25IND023 | Steel : Introduction of Laxmi Steel | Steel-GI | Central Procurement | IND | Central | III: Alternative Sourcing (Conditions or Security) | NO | n/a | NO | n/a | in BDG | Jan_25 | 63 | 63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | HI | 100% | 100% | 0% | 0% | 0% |  | 3
25SRC046 | Silk Print | Silk Screened Parts | Central Sourcing | SRC | Central | III: Alternative Sourcing (Conditions or Security) | 0 | 0 | 0 | 0 | in BDG | Sep_25 | 5.9259 | 1.1852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50% share - not started | MED | 60% | 0% | 0% | 0% | 0% |  | 2
25SRC045 | Silicone | Silicones | Central Sourcing | SRC | Central | III: Alternative Sourcing (Conditions or Security) | 0 | 0 | 0 | 0 | in BDG | Sep_25 | 3.3104 | 0.66208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50% share - not started | MED | 60% | 0% | 0% | 0% | 0% |  | 2
25IND022 | Wire Shelf : New Supplier Development Secom -> Bedi Wire/SR Fabrication | Shelves | Central Procurement | IND | Central | III: Alternative Sourcing (Conditions or Security) | NO | n/a | NO | n/a | in BDG | Jan_25 | 3.808 | 3.808 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | HI | 100% | 100% | 0% | 0% | 0% |  | 3
24SRC078 | Shaded pole motor Saiwei as altearnative to Weigung YZF10-20 | Shaded Pole Motors & Blades | Central Sourcing | SRC | Central | III: Alternative Sourcing (Conditions or Security) | 0 | 0 | 0 | 0 | in BDG | Jan_25 | 43.453 | 43.453 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50% share | HI | 80% | 80% | 10% | 0% | 10% |  | 3
24SRC079 | Shaded pole motor Saiwei as altearnative to Weigung YZF16-25 | Shaded Pole Motors & Blades | Central Sourcing | SRC | Central | III: Alternative Sourcing (Conditions or Security) | 0 | 0 | 0 | 0 | in BDG | Jan_25 | 14.88 | 14.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50% share | HI | 80% | 50% | 0% | 20% | 30% |  | 3
25IND021 | Refrigerant Gases : Alternate Supplier Development Star Special -> Helious | Refrigerants | Central Procurement | IND | Central | III: Alternative Sourcing (Conditions or Security) | NO | n/a | NO | n/a | in BDG | Feb_25 | 1 | 0.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | MED | 90% | 100% | 0% | 0% | 0% |  | 2
24SRC077 | PSU Done as alternative to Tauras for 12W | PSU | Central Sourcing | SRC | Central | III: Alternative Sourcing (Conditions or Security) | 0 | 0 | 0 | 0 | in BDG | Mar_25 | 7.798 | 6.2384 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60% share | HI | 80% | 0% | 30% | 70% | 0% |  | 3
24SRC075 | PSU Done as alternative to Tauras for 15/16W | PSU | Central Sourcing | SRC | Central | III: Alternative Sourcing (Conditions or Security) | 0 | 0 | 0 | 0 | in BDG | Mar_25 | 37.367 | 29.8936 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60% share | HI | 80% | 0% | 10% | 90% | 0% |  | 3
24SRC076 | PSU Done as alternative to Tauras for 20W | PSU | Central Sourcing | SRC | Central | III: Alternative Sourcing (Conditions or Security) | 0 | 0 | 0 | 0 | in BDG | Mar_25 | 10.118 | 8.0944 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60% share | HI | 80% | 0% | 20% | 30% | 50% |  | 3
25SRC044 | PSU Tauras as alternative supplier for Meanwell 12W | PSU | Central Sourcing | SRC | Central | III: Alternative Sourcing (Conditions or Security) | 0 | 0 | 0 | 0 | in BDG | Jan_25 | 32.999 | 32.999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60% share | MED | 80% | 100% | 0% | 0% | 0% |  | 2
25SRC043 | PSU Tauras as alternative supplier for Meanwell 16W | PSU | Central Sourcing | SRC | Central | III: Alternative Sourcing (Conditions or Security) | 0 | 0 | 0 | 0 | in BDG | Jan_25 | 50.985 | 50.985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60% share | MED | 80% | 100% | 0% | 0% | 0% |  | 2
25CPG003 | Blue Line 3 years contract (IND) | Protector - Stabilizer | Central Procurement | CPG | Central | I: Conditions or Specs Negotiation | NO | n/a | NO | n/a | in BDG | Jan_25 | 60 | 60 | 0 | 0 | 0 | 0 | 0 | Not_Started | Not_Started | 0 |  | HI | 80% | 100% | 0% | 0% | 0% |  | 3
25IND019 | Di-cals & Labels : New Supplier Development Nitin AD -> Retail Junction | Printing Materials | Central Procurement | IND | Central | III: Alternative Sourcing (Conditions or Security) | NO | n/a | NO | n/a | in BDG | Jan_25 | 16.6667 | 16.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | HI | 100% | 100% | 0% | 0% | 0% |  | 3
25IND020 | Stickers and labels : Multi Suppliers to MD Graphic(7-8 Suppliers) | Printing Materials | Central Procurement | IND | Central | III: Alternative Sourcing (Conditions or Security) | NO | n/a | NO | n/a | in BDG | Jan_25 | 3.5556 | 3.5556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | HI | 80% | 100% | 0% | 0% | 0% |  | 3
25SRC042 | Stretch Film Reel | Plastic bags & Stretch Film | Central Sourcing | SRC | Central | III: Alternative Sourcing (Conditions or Security) | 0 | 0 | 0 | 0 | in BDG | Sep_25 | 4.4563 | 0.89127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50% share - not started | MED | 60% | 0% | 0% | 0% | 0% |  | 2
24SRC074 | ACE (China) Metal Handle | Metal Processing & Components | Central Sourcing | SRC | Central | III: Alternative Sourcing (Conditions or Security) | 0 | 0 | 0 | 0 | in BDG | Jan_25 | 36.48 | 36.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60% share | MED | 80% | 0% | 0% | 100% | 0% |  | 2
24SRC072 | Ace (China) Shelf Clip | Metal Processing & Components | Central Sourcing | SRC | Central | III: Alternative Sourcing (Conditions or Security) | 0 | 0 | 0 | 0 | in BDG | Jan_25 | 75.06 | 75.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60% share | MED | 80% | 0% | 0% | 100% | 0% |  | 2
24SRC073 | ACE (China) Top Hinge | Metal Processing & Components | Central Sourcing | SRC | Central | III: Alternative Sourcing (Conditions or Security) | 0 | 0 | 0 | 0 | in BDG | Jan_25 | 50.4 | 50.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60% share | MED | 80% | 0% | 0% | 100% | 0% |  | 2
25SAF007 | Alternate supplier for Metal Processing & Components in S.A | Metal Processing & Components | Central Procurement | SAF | Central | III: Alternative Sourcing (Conditions or Security) | 0 | 0 | 0 | 0 | in BDG | Apr_25 | 125 | 93.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Awaiting Supplier costing, Requirment and confirmed Lead time, 'Support from Production and PD/ENG for sample & FPAP | HI | 90% | 0% | 0% | 0% | 100% | Provide supplier with respective drawings and annual Vol. Awaiting for supplier response & confirmation that they can deliver our requirement while meeting our quality expectations. Verify supplier drawings with Frigoglass(Evidence).Negotiate Pricing and secure savings. Receive samples and perform FPAP and upon approval receive pilot order | 3
25IND017 | HINGES : Nego - 4 % with existing supplier Matangi Or New supplier add | Metal Processing & Components | Central Procurement | IND | Central | III: Alternative Sourcing (Conditions or Security) | NO | n/a | NO | n/a | in BDG | Apr_25 | 4.3333 | 2.8167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | HI | 100% | 100% | 0% | 0% | 0% |  | 3
25SRC040 | Lock Metal Parts | Metal Processing & Components | Central Sourcing | SRC | Central | III: Alternative Sourcing (Conditions or Security) | 0 | 0 | 0 | 0 | in BDG | Sep_25 | 4.3479 | 0.86958 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50% share - not started | MED | 60% | 0% | 0% | 0% | 0% |  | 2
24SRC071 | Nisiki (india) Fan Grid | Metal Processing & Components | Central Sourcing | SRC | Central | III: Alternative Sourcing (Conditions or Security) | 0 | 0 | 0 | 0 | in BDG | Jan_25 | 123.7 | 123.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% share | MED | 90% | 0% | 0% | 100% | 0% |  | 2
25IND016 | Press Components : New Supplier Development RK Ent -> Radical Components | Metal Processing & Components | Central Procurement | IND | Central | III: Alternative Sourcing (Conditions or Security) | NO | n/a | NO | n/a | in BDG | Jan_25 | 8.3333 | 8.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | MED | 90% | 100% | 0% | 0% | 0% |  | 2
25SAF008 | Revisit local shelf clip option | Metal Processing & Components | Local R&PD | SAF | Local | I: Conditions or Specs Negotiation | 0 | 0 | 0 | 0 | in BDG | Jul_25 | 7.3 | 3.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Investigating local supplier | HI | 90% | 0% | 0% | 0% | 100% | supplier currentlry doing sample | 3
25SRC039 | Rollers | Metal Processing & Components | Central Sourcing | SRC | Central | III: Alternative Sourcing (Conditions or Security) | 0 | 0 | 0 | 0 | in BDG | Apr_25 | 10.75 | 7.525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50% share | HI | 80% | 0% | 0% | 100% | 0% |  | 3
25SRC038 | Shelf Pillaster | Metal Processing & Components | Central Sourcing | SRC | Central | III: Alternative Sourcing (Conditions or Security) | 0 | 0 | 0 | 0 | in BDG | Apr_25 | 41.75 | 29.225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50% share | MED | 80% | 0% | 0% | 100% | 0% |  | 2
25SRC041 | Spring | Metal Processing & Components | Central Sourcing | SRC | Central | III: Alternative Sourcing (Conditions or Security) | 0 | 0 | 0 | 0 | in BDG | Sep_25 | 3.0646 | 0.61291 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50% share - not started | MED | 60% | 0% | 0% | 0% | 0% |  | 2
25IND018 | Top Hinge (Single Source) : Alternate Supplier Development DPK -> Under evaluation | Metal Processing & Components | Central Procurement | IND | Central | III: Alternative Sourcing (Conditions or Security) | NO | n/a | NO | n/a | in BDG | Jan_25 | 0.22778 | 0.22778 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | MED | 70% | 100% | 0% | 0% | 0% |  | 2
25IND015 | Armaflex Tube : Alternate Supplier Development Ajay Poly -> Vaishno India | Magnetic Gaskets | Central Procurement | IND | Central | III: Alternative Sourcing (Conditions or Security) | NO | n/a | NO | n/a | in BDG | Jan_25 | 3.2222 | 3.2222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | HI | 100% | 100% | 0% | 0% | 0% |  | 3
25IND014 | Gasket & Extrusion : In-House Development Ajay Poly -> Sudarshan (In-house) | Magnetic Gaskets | Central Procurement | IND | Central | III: Alternative Sourcing (Conditions or Security) | NO | n/a | NO | n/a | in BDG | Jan_25 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | HI | 90% | 100% | 0% | 0% | 0% |  | 3
25IND013 | I-Lock(Blue Star) : New Supplier Development Keyman -> Noble Lock | Locks | Central Procurement | IND | Central | III: Alternative Sourcing (Conditions or Security) | NO | n/a | NO | n/a | in BDG | Jan_25 | 9.7222 | 9.7222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | MED | 70% | 100% | 0% | 0% | 0% |  | 2
25SRC036 | LED Conrun as alternative to Refond 1200mm | LED | Central Sourcing | SRC | Central | III: Alternative Sourcing (Conditions or Security) | 0 | 0 | 0 | 0 | in BDG | Mar_25 | 1.333 | 1.0664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60% share | HI | 80% | 0% | 0% | 0% | 100% |  | 3
25SRC035 | LED Conrun as alternative to Refond 1400mm | LED | Central Sourcing | SRC | Central | III: Alternative Sourcing (Conditions or Security) | 0 | 0 | 0 | 0 | in BDG | Mar_25 | 12.92 | 10.336 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60% share | HI | 80% | 0% | 0% | 0% | 100% |  | 3
25SRC037 | LED Conrun as alternative to Refond 800mm | LED | Central Sourcing | SRC | Central | III: Alternative Sourcing (Conditions or Security) | 0 | 0 | 0 | 0 | in BDG | Mar_25 | 0.844 | 0.6752 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60% share | HI | 80% | 0% | 0% | 0% | 100% |  | 3
24SRC069 | LED Conrun as alternative to Refond for 1600mm low cost | LED | Central Sourcing | SRC | Central | III: Alternative Sourcing (Conditions or Security) | 0 | 0 | 0 | 0 | in BDG | Jan_25 | 3.3 | 3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60% share | HI | 80% | 0% | 0% | 100% | 0% |  | 3
24SRC064 | LED Conrun as alternative to Refond for 1600mm low wattage | LED | Central Sourcing | SRC | Central | IV: Sourcing (Technology, Conditions or Security) | 0 | 0 | 0 | 0 | in BDG | Jan_25 | 18.1 | 18.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60% share | HI | 80% | 0% | 0% | 100% | 0% |  | 3
24SRC066 | LED Conrun as alternative to Refond for 1600mm standard | LED | Central Sourcing | SRC | Central | III: Alternative Sourcing (Conditions or Security) | 0 | 0 | 0 | 0 | in BDG | Jan_25 | 13.2 | 13.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60% share | HI | 80% | 0% | 0% | 100% | 0% |  | 3
24SRC067 | LED Conrun as alternative to Refond for 1800mm low cost | LED | Central Sourcing | SRC | Central | III: Alternative Sourcing (Conditions or Security) | 0 | 0 | 0 | 0 | in BDG | Jan_25 | 4.5 | 4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60% share | HI | 80% | 0% | 0% | 100% | 0% |  | 3
24SRC065 | LED Conrun as alternative to Refond for 1800mm low wattage | LED | Central Sourcing | SRC | Central | IV: Sourcing (Technology, Conditions or Security) | 0 | 0 | 0 | 0 | in BDG | Jan_25 | 14.8 | 14.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60% share | HI | 80% | 0% | 0% | 100% | 0% |  | 3
24SRC068 | LED Conrun as alternative to Refond for 1800mm standard | LED | Central Sourcing | SRC | Central | III: Alternative Sourcing (Conditions or Security) | 0 | 0 | 0 | 0 | in BDG | Jan_25 | 3.3 | 3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60% share | HI | 80% | 0% | 0% | 100% | 0% |  | 3
24SRC070 | LED Conrun as alternative to Refond for 400mm low cost | LED | Central Sourcing | SRC | Central | III: Alternative Sourcing (Conditions or Security) | 0 | 0 | 0 | 0 | in BDG | Jan_25 | 0.7 | 0.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60% share | HI | 80% | 0% | 0% | 100% | 0% |  | 3
25SRC033 | Documents | Labels & Manuals | Central Sourcing | SRC | Central | III: Alternative Sourcing (Conditions or Security) | 0 | 0 | 0 | 0 | in BDG | Sep_25 | 8.2721 | 1.6544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50% share - not started | MED | 60% | 0% | 0% | 0% | 0% |  | 2
25SAF006 | Non CCBSA Artwork Supplier | Labels & Manuals | Central Procurement | SAF | Central | III: Alternative Sourcing (Conditions or Security) | 0 | 0 | 0 | 0 | in BDG | Mar_25 | 11 | 9.1667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Awaiting Supplier costing, Requirment and confirmed Lead time, 'Support from Production and PD/ENG for sample & FPAP | HI | 90% | 0% | 0% | 0% | 100% | Provide supplier with respective drawings and annual Vol. Awaiting for supplier response & confirmation that they can deliver our requirement while meeting our quality expectations. Verify supplier drawings with Frigoglass(Evidence).Negotiate Pricing and secure savings. Receive samples and perform FPAP and upon approval receive pilot order | 3
25SRC034 | Stickers | Labels & Manuals | Central Sourcing | SRC | Central | III: Alternative Sourcing (Conditions or Security) | 0 | 0 | 0 | 0 | in BDG | Sep_25 | 7.4886 | 1.4977 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50% share - not started | MED | 60% | 0% | 0% | 0% | 0% |  | 2
25SAF004 | Localization for Drip Tray | Injection Plastics | Central Procurement | SAF | Central | III: Alternative Sourcing (Conditions or Security) | 0 | 0 | 0 | 0 | in BDG | Mar_25 | 5 | 4.1667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Awaiting Supplier costing, Requirment and confirmed Lead time, 'Support from Production and PD/ENG for sample & FPAP | MED | 60% | 0% | 0% | 0% | 100% | Provide supplier with respective drawings and annual Vol. Awaiting for supplier response & confirmation that they can deliver our requirement while meeting our quality expectations. Verify supplier drawings with Frigoglass(Evidence).Negotiate Pricing and secure savings. Receive samples and perform FPAP and upon approval receive pilot order | 2
25SAF005 | Plastic Evap Fan Grill Localization | Injection Plastics | Local R&PD | SAF | Local | III: Alternative Sourcing (Conditions or Security) | 0 | 0 | 0 | 0 | in BDG | Apr_25 | 10 | 7.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Investigating supplier that has the capability to provide this by 23 September 2024 | HI | 80% | 0% | 0% | 0% | 100% | Sourcing in progress | 3
25IND012 | Plastic Moulding parts : Alternate Supplier Development EIC & Geeta/Everfine -> Under evaluation | Injection Plastics | Central Procurement | IND | Central | III: Alternative Sourcing (Conditions or Security) | NO | n/a | NO | n/a | in BDG | Jan_25 | 4.4444 | 4.4444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | HI | 90% | 100% | 0% | 0% | 0% |  | 3
24SRC061 | Condenser Flygrow as alternative to Konveyor for IC2-300 | HEX | Central Sourcing | SRC | Central | III: Alternative Sourcing (Conditions or Security) | 0 | 0 | 0 | 0 | in BDG | Jan_25 | 17.5 | 17.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60% share | HI | 80% | 0% | 0% | 100% | 0% |  | 3
24SRC059 | Condenser Flygrow as alternative to Konveyor for Max-700C | HEX | Central Sourcing | SRC | Central | III: Alternative Sourcing (Conditions or Security) | 0 | 0 | 0 | 0 | in BDG | Jan_25 | 29.5 | 29.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60% share | HI | 80% | 0% | 0% | 100% | 0% |  | 3
24SRC057 | Evaporator Flygrow as alternative to Clad Metal for Max-450B | HEX | Central Sourcing | SRC | Central | III: Alternative Sourcing (Conditions or Security) | 0 | 0 | 0 | 0 | in BDG | Jan_25 | 94.9 | 94.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60% share | HI | 80% | 0% | 0% | 100% | 0% |  | 3
24SRC062 | Evaporator Flygrow as alternative to Konveyor for IC2-300B | HEX | Central Sourcing | SRC | Central | IV: Sourcing (Technology, Conditions or Security) | 0 | 0 | 0 | 0 | in BDG | Jan_25 | 12.7 | 12.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60% share | HI | 80% | 0% | 0% | 100% | 0% |  | 3
24SRC063 | Evaporator Flygrow as alternative to Konveyor for IC2-800B | HEX | Central Sourcing | SRC | Central | IV: Sourcing (Technology, Conditions or Security) | 0 | 0 | 0 | 0 | in BDG | Jan_25 | 11.4 | 11.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60% share | HI | 80% | 0% | 0% | 100% | 0% |  | 3
24SRC058 | Evaporator Flygrow as alternative to Konveyor for Max-450C | HEX | Central Sourcing | SRC | Central | IV: Sourcing (Technology, Conditions or Security) | 0 | 0 | 0 | 0 | in BDG | Jan_25 | 30.8 | 30.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60% share | HI | 80% | 0% | 0% | 100% | 0% |  | 3
24SRC060 | Evaporator Flygrow as alternative to Konveyor for Max-700C | HEX | Central Sourcing | SRC | Central | IV: Sourcing (Technology, Conditions or Security) | 0 | 0 | 0 | 0 | in BDG | Jan_25 | 27.2 | 27.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60% share | HI | 80% | 0% | 0% | 100% | 0% |  | 3
24SRC056 | Evaporator Flygrow as alternative to Konveyor for Plus-900B | HEX | Central Sourcing | SRC | Central | III: Alternative Sourcing (Conditions or Security) | 0 | 0 | 0 | 0 | in BDG | Jan_25 | 103.1 | 103.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60% share | HI | 80% | 0% | 0% | 100% | 0% |  | 3
25IND011 | HEX : Copper Joint pipe length will reduce (From 345mm to 295mm) | HEX | Central Procurement | IND | Central | I: Conditions or Specs Negotiation | YES | NO | NO | n/a | in BDG | Apr_25 | 9.3333 | 6.0667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | HI | 90% | 100% | 0% | 0% | 0% |  | 3
25SAF003 | Localization for Evaporators | HEX | Central Procurement | SAF | Central | III: Alternative Sourcing (Conditions or Security) | 0 | 0 | 0 | 0 | in BDG | Jun_25 | 12 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Awaiting Supplier costing, Requirment and confirmed Lead time, 'Support from Production and PD/ENG for sample & FPAP | MED | 60% | 0% | 0% | 0% | 100% | Provide supplier with respective drawings and annual Vol. Awaiting for supplier response & confirmation that they can deliver our requirement while meeting our quality expectations. Verify supplier drawings with Frigoglass(Evidence).Negotiate Pricing and secure savings. Receive samples and perform FPAP and upon approval receive pilot order | 2
25SRC032 | Fastenings for S.Africa from China | Fastening Materials | Central Sourcing | SRC | Local | III: Alternative Sourcing (Conditions or Security) | 0 | 0 | 0 | 0 | in BDG | Jan_25 | 24.65 | 24.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40% share | MED | 90% | 0% | 0% | 0% | 100% |  | 2
25IND010 | Hardware : Alternate Supplier Development Hydrau & RS tools -> Advance Dynamic | Fastening Materials | Central Procurement | IND | Central | III: Alternative Sourcing (Conditions or Security) | NO | n/a | NO | n/a | in BDG | Jan_25 | 4.4444 | 4.4444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | HI | 90% | 100% | 0% | 0% | 0% |  | 3
25ROM004 | Validate alternative supplier (new Bossard Vs. Bolhoff) | Fastening Materials | Central Procurement | ROM | Central | III: Alternative Sourcing (Conditions or Security) | 0 | 0 | 0 | 0 | in BDG | Jan_25 | 42.1564 | 42.1564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | share business Bossard 85% (new supplier) and Bollhoff 15% (actual supplier) | HI | 90% | 0% | 0% | 100% | 0% | 'to finalise the validation of Bossard; procurement to finalise the the agreement with Bossard, the share of business with SC for implementation | 3
25SRC031 | Insulation Tube | Extrusion pl. Profiles | Central Sourcing | SRC | Central | III: Alternative Sourcing (Conditions or Security) | 0 | 0 | 0 | 0 | in BDG | Jan_25 | 5.45 | 5.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50% share | MED | 80% | 0% | 0% | 100% | 0% |  | 2
25IND009 | EPS : Alternate Supplier Development Excel styropack -> Parmar Ind. | EPS | Central Procurement | IND | Central | III: Alternative Sourcing (Conditions or Security) | NO | n/a | NO | n/a | in BDG | Jan_25 | 1.1111 | 1.1111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | HI | 80% | 100% | 0% | 0% | 0% |  | 3
24SRC055 | Electronic motor Saiwei NEC4810 as alternative to Weiguang ECM7112 | Electronic Motors | Central Sourcing | SRC | Central | III: Alternative Sourcing (Conditions or Security) | 0 | 0 | 0 | 0 | in BDG | Jan_25 | 9.449 | 9.449 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50% share | HI | 80% | 70% | 0% | 0% | 30% |  | 3
24SRC054 | Electronic motor Saiwei NEC6115 as alternative to Weiguang ECM7120 | Electronic Motors | Central Sourcing | SRC | Central | III: Alternative Sourcing (Conditions or Security) | 0 | 0 | 0 | 0 | in BDG | Jan_25 | 9.799 | 9.799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50% share | HI | 80% | 0% | 40% | 0% | 60% |  | 3
25SRC027 | Controller Keepthink as alternative to CAREL | Electronic Controllers & Acces | Central Sourcing | SRC | Central | III: Alternative Sourcing (Conditions or Security) | 0 | 0 | 0 | 0 | in BDG | Mar_25 | 43.4 | 34.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40% share | MED | 60% | 0% | 0% | 100% | 0% |  | 2
25SRC029 | Probe Keepthink as alternative to CAREL | Electronic Controllers & Acces | Central Sourcing | SRC | Central | III: Alternative Sourcing (Conditions or Security) | 0 | 0 | 0 | 0 | in BDG | Mar_25 | 2.1 | 1.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40% share | MED | 60% | 0% | 0% | 100% | 0% |  | 2
25SRC028 | Reed switch Ease as alternative to ACEE for 0.4m cable | Electronic Controllers & Acces | Central Sourcing | SRC | Central | III: Alternative Sourcing (Conditions or Security) | 0 | 0 | 0 | 0 | in BDG | Jan_25 | 26.3 | 26.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50% share | HI | 80% | 0% | 0% | 100% | 0% |  | 3
25SRC030 | Reed switch Ease as alternative to ACEE for 1m cable | Electronic Controllers & Acces | Central Sourcing | SRC | Central | III: Alternative Sourcing (Conditions or Security) | 0 | 0 | 0 | 0 | in BDG | Jan_25 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50% share | HI | 80% | 0% | 0% | 100% | 0% |  | 3
24SRC053 | Kuxan (China) Connectors | Electrical Components | Central Sourcing | SRC | Central | III: Alternative Sourcing (Conditions or Security) | 0 | 0 | 0 | 0 | in BDG | Jan_25 | 17.4 | 17.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% share | HI | 90% | 0% | 0% | 100% | 0% |  | 3
25IND008 | On/Off Switch : New Supplier Development Promark -> Under Evaluation | Electrical Components | Central Procurement | IND | Central | III: Alternative Sourcing (Conditions or Security) | NO | n/a | NO | n/a | in BDG | Jul_25 | 0.053167 | 0.053167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | MED | 70% | 100% | 0% | 0% | 0% |  | 2
25SRC023 | Power Cable | Electrical Components | Central Sourcing | SRC | Central | III: Alternative Sourcing (Conditions or Security) | 0 | 0 | 0 | 0 | in BDG | Jan_25 | 16.15 | 16.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50% share | MED | 80% | 0% | 0% | 100% | 0% |  | 2
25SRC026 | Switch | Electrical Components | Central Sourcing | SRC | Central | III: Alternative Sourcing (Conditions or Security) | 0 | 0 | 0 | 0 | in BDG | Sep_25 | 1.8119 | 0.36238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50% share - not started | MED | 60% | 0% | 0% | 0% | 0% |  | 2
25SRC024 | Terminal block | Electrical Components | Central Sourcing | SRC | Central | III: Alternative Sourcing (Conditions or Security) | 0 | 0 | 0 | 0 | in BDG | Sep_25 | 10 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50% share - not started | MED | 60% | 0% | 0% | 0% | 0% |  | 2
25SRC025 | Thermal Circuit Breaker | Electrical Components | Central Sourcing | SRC | Central | III: Alternative Sourcing (Conditions or Security) | 0 | 0 | 0 | 0 | in BDG | Sep_25 | 4.3185 | 0.86369 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50% share - not started | MED | 60% | 0% | 0% | 0% | 0% |  | 2
25SAF002 | 1/4" Copper tube thickness reduction from 0.76 to 0.65mm | Copper Tubes | R&PD and PRC | SAF | Central | I: Conditions or Specs Negotiation | 0 | 0 | 0 | 0 | in BDG | Apr_25 | 15 | 11.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Awaiting installation of the new machine (BLM) | HI | 100% | 0% | 0% | 0% | 100% | Machine at Port, Awaiting release | 3
25CPG004 | Capillary tubes: Konveyor(TR) as alternative supplier to HME Spain | Copper Tubes | Central Procurement | CPG | Central | III: Alternative Sourcing (Conditions or Security) | 0 | 0 | 0 | 0 | in BDG | Mar_25 | 1.76 | 1.232 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Price formula. Saving of €0.55 is FAB/kg, compared with current supply source and assuming 40% SOB allocation. | MED | 70% | 0% | 0% | 100% | 0% | 1.NDA has been signed and stamped 2.Konveyor visited HO at w37 to discuss terms and conditions for 24.(demand has been shared) 3.Once T&Cs are agreed, RFQ to be signed and stamped from both sides and FSA as well. 4.In parallel, samples to be requested for testing 5.Once green light is received by technical team for using for main production, pilot order should be placed. 6.SOB to submitted and confirmed 7.Start ordering for pilot order and once final approval if shared, start for main prodcution | 2
25SRC022 | Copper Tube Haike as alternative to Golden Dragon | Copper Tubes | Central Sourcing | SRC | Central | III: Alternative Sourcing (Conditions or Security) | 0 | 0 | 0 | 0 | in BDG | Jan_25 | 1.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50% share (fabrication cost) | HI | 80% | 0% | 0% | 70% | 0% |  | 3
25IND004 | Capillary Tube : Dual sourcing for Capillary (Pallavi -> Pallavi/ KPM ) | Copper Components | Central Procurement | IND | Central | III: Alternative Sourcing (Conditions or Security) | NO | n/a | NO | n/a | in BDG | Feb_25 | 1.7736 | 1.2415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | HI | 80% | 100% | 0% | 0% | 0% |  | 3
25CPG005 | Competitive alternative in EU/TR for accumulators and filter dryers Vs. General Filter | Copper Components | Central Procurement | CPG | Central | III: Alternative Sourcing (Conditions or Security) | 0 | 0 | 0 | 0 | in BDG | Apr_25 | 2.935 | 1.761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Price formula. Saving of 0,06 €/pc (for 15GR filter dryer) and 0,06€/pc (for accumulator D30/110mm), compared with current source and assuming 40% SOB allocation. | MED | 60% | 0% | 0% | 100% | 0% | 1.Contact EU/TR supplier 2.Sign NDA 3.In parallel, order samples 4.Agree on T&Cs 5.Sign RFQ and FSA 6.SOB to defined and confirmed 7.Once technical approval is shared, start with pilot order 8. Final approved is shared, then we can start with main production orders. | 2
25IND005 | Copper Parts : Dual sourcing for Driers and accumulators (SVS -> SVS & KPM) | Copper Components | Central Procurement | IND | Central | III: Alternative Sourcing (Conditions or Security) | NO | n/a | NO | n/a | in BDG | Feb_25 | 1.1538 | 0.80769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | HI | 100% | 100% | 0% | 0% | 0% |  | 3
25SRC008 | Compressor Donper L76CU1 as alternative to Huayi NUY80RAa | Compressors | Central Sourcing | SRC | Central | III: Alternative Sourcing (Conditions or Security) | 0 | 0 | 0 | 0 | in BDG | Mar_25 | 63.62 | 44.534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90% share | HI | 80% | 0% | 0% | 100% | 0% |  | 3
25SRC011 | Compressor Donper L83CU1 as alternative to Huayi NUY90RAb | Compressors | Central Sourcing | SRC | Central | III: Alternative Sourcing (Conditions or Security) | 0 | 0 | 0 | 0 | in BDG | Mar_25 | 37.909 | 26.5363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90% share | HI | 80% | 0% | 0% | 100% | 0% |  | 3
25SRC004 | Compressor Donper LZ76CU1 as alternative to Huayi NUS70NA | Compressors | Central Sourcing | SRC | Central | III: Alternative Sourcing (Conditions or Security) | 0 | 0 | 0 | 0 | in BDG | Mar_25 | 295.287 | 206.7009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% share | HI | 80% | 0% | 0% | 0% | 100% |  | 3
25SRC017 | Compressor Donper LZ83WU1 as alternative to TCW420-UZ3B | Compressors | Central Sourcing | SRC | Central | III: Alternative Sourcing (Conditions or Security) | 0 | 0 | 0 | 0 | in BDG | Jun_25 | 8.329 | 2.4987 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50% share | HI | 80% | 100% | 0% | 0% | 0% |  | 3
25SRC013 | Compressor Donper SU50DU1 as alternative to Wanbao FTA45L | Compressors | Central Sourcing | SRC | Central | III: Alternative Sourcing (Conditions or Security) | 0 | 0 | 0 | 0 | in BDG | Apr_25 | 30.176 | 18.1056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90% share | HI | 80% | 0% | 0% | 100% | 0% |  | 3
25SRC014 | Compressor GMCC PZ99HMC as alternative to Wanbao FTB45 | Compressors | Central Sourcing | SRC | Central | III: Alternative Sourcing (Conditions or Security) | 0 | 0 | 0 | 0 | in BDG | Apr_25 | 19.347 | 11.6082 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90% share | MED | 80% | 0% | 0% | 100% | 0% |  | 2
25SRC015 | Compressor Tecumseh TCW380U-MR3B to substitute Tecumseh THK9384-YCG | Compressors | Central Sourcing | SRC | Central | IV: Sourcing (Technology, Conditions or Security) | 0 | 0 | 0 | 0 | in BDG | Jan_25 | 15.5 | 15.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% share | HI | 80% | 100% | 0% | 0% | 0% |  | 3
25SRC020 | Compressor Tecumseh TCW380U-MR3B to substitute Tecumseh THK9414 | Compressors | Central Sourcing | SRC | Central | IV: Sourcing (Technology, Conditions or Security) | 0 | 0 | 0 | 0 | in BDG | Jan_25 | 4.6 | 4.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% share | HI | 80% | 100% | 0% | 0% | 0% |  | 3
25SRC018 | Compressor Tecumseh TCW410U-CE3A to substitute Tecumseh THK9412-YJE | Compressors | Central Sourcing | SRC | Central | IV: Sourcing (Technology, Conditions or Security) | 0 | 0 | 0 | 0 | in BDG | Jan_25 | 8.048 | 8.048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% share | HI | 80% | 100% | 0% | 0% | 0% |  | 3
25SRC016 | Compressor Tecumseh TCW415U-CE3A to substitute Tecumseh THK9417-YJE | Compressors | Central Sourcing | SRC | Central | IV: Sourcing (Technology, Conditions or Security) | 0 | 0 | 0 | 0 | in BDG | Jan_25 | 14.8 | 14.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% share | HI | 80% | 100% | 0% | 0% | 0% |  | 3
25SRC021 | Compressor Tecumseh TCW420U-UZ3B to substitute Tecumseh AE4440Y-GH3C | Compressors | Central Sourcing | SRC | Central | IV: Sourcing (Technology, Conditions or Security) | 0 | 0 | 0 | 0 | in BDG | Jan_25 | 4.2 | 4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% share | HI | 80% | 100% | 0% | 0% | 0% |  | 3
25SRC012 | Compressor Tecumseh TCW420U-UZ3B to substitute Tecumseh AE4460Y-FZ | Compressors | Central Sourcing | SRC | Central | IV: Sourcing (Technology, Conditions or Security) | 0 | 0 | 0 | 0 | in BDG | Jan_25 | 36.8 | 36.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% share | HI | 80% | 100% | 0% | 0% | 0% |  | 3
25CPG001 | Replace NIDEC variable speed (ROM) | Compressors | Central Procurement | CPG | Central | III: Alternative Sourcing (Conditions or Security) | YES | NO | YES | NO | in BDG | May_25 | 525 | 315 | 0 | 0 | 0 | 0 | 0 | RFQ Completed | Internal In_Process | 0 |  | MED | 100% | 0% | 0% | 100% | 0% |  | 2
25SRC003 | Carton Box & Corner | Carton box | Central Sourcing | SRC | Central | III: Alternative Sourcing (Conditions or Security) | 0 | 0 | 0 | 0 | in BDG | Sep_25 | 5.3896 | 1.0779 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50% share - not started | MED | 60% | 0% | 0% | 0% | 0% |  | 2
25ROM003 | Validate alternative supplier (new Vs. Ambro) | Carton box | Central Procurement | ROM | Central | III: Alternative Sourcing (Conditions or Security) | 0 | 0 | 0 | 0 | in BDG | Apr_25 | 9 | 6.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | estimated saving of 10% with SOB 50 % | MED | 80% | 0% | 0% | 100% | 0% | specs confirmation(TDS,drawings), sourcing , evaluation, validation, implementation | 2
24SRC052 | CABLEX (Slovenia) - Cables | Cable Harnesses | Central Sourcing | SRC | Central | III: Alternative Sourcing (Conditions or Security) | 0 | 0 | 0 | 0 | in BDG | Jan_25 | 42.8164 | 42.8164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% share | HI | 80% | 0% | 0% | 100% | 0% |  | 3
25SAF001 | Condernsor fan motor cable optimization | Cable Harnesses | Local R&PD | SAF | Local | I: Conditions or Specs Negotiation | 0 | 0 | 0 | 0 | in BDG | Apr_25 | 16 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Currently depleting cable stocks | HI | 100% | 0% | 0% | 0% | 100% | Cooling system sampling in progress | 3
25ROM002 | Validate alternative supplier (new Image Quality Vs. Monita) | Cable Harnesses | Central Procurement | ROM | Central | III: Alternative Sourcing (Conditions or Security) | 0 | 0 | 0 | 0 | in BDG | Jan_25 | 65.9959 | 65.9959 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | oportunity with image quality 10 % for all the harnesses and share of business 50 % / 50% | HI | 90% | 0% | 0% | 100% | 0% | To finlaise the validation of Image Quality, to agree the share of business (SC, PD, Qulaity, cooler types implementation); procuremnet to finalise the RFQ | 3
25IND003 | Wire Harness : Alternate Supplier Develop EI -> ITP / KPM | Cable Harnesses | Central Procurement | IND | Central | III: Alternative Sourcing (Conditions or Security) | NO | n/a | NO | n/a | in BDG | Jan_25 | 17.6906 | 17.6906 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | HI | 90% | 100% | 0% | 0% | 0% |  | 3
25SRC002 | Soldering Wire | Brazing materials | Central Sourcing | SRC | Central | III: Alternative Sourcing (Conditions or Security) | 0 | 0 | 0 | 0 | in BDG | Sep_25 | 2.69 | 0.538 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50% share - not started | MED | 60% | 0% | 0% | 0% | 0% |  | 2
25ROM001 | Validate alternative supplier (new Sentes Vs. Voestelpine) | Brazing materials | Central Procurement | ROM | Central | III: Alternative Sourcing (Conditions or Security) | 0 | 0 | 0 | 0 | in BDG | Jan_25 | 17.9543 | 17.9543 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | calculation based on offer 05.08.2024; share of business 70% | HI | 90% | 0% | 0% | 100% | 0% | to discuss with SC the implementation (set up the supplier data in ERP, confirm share of business); procurment to finalise agreement related to MOQ and payment term) | 0
24SRC050 | EC block motor Rexnord EC-12038 S0WMP 02 as alternative to Nisiki NIS12038HS2W-EC | Block Motors | Central Sourcing | SRC | Central | III: Alternative Sourcing (Conditions or Security) | 0 | 0 | 0 | 0 | in BDG | Jan_25 | 94.905 | 94.905 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50% share | HI | 80% | 30% | 10% | 50% | 10% |  | 3
24SRC051 | Jinjiu (China) - AC Block Motors 120X120X38 | Block Motors | Central Sourcing | SRC | Central | III: Alternative Sourcing (Conditions or Security) | 0 | 0 | 0 | 0 | in BDG | Jan_25 | 19.2 | 19.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40% share | MED | 90% | 100% | 0% | 0% | 0% |  | 2
25IND002 | Motors : Alternate Supplier Development Hicool/Micro/Rexnord -> Under evaluation | Block Motors | Central Procurement | IND | Central | III: Alternative Sourcing (Conditions or Security) | YES | NO | NO | n/a | in BDG | Jul_25 | 13.3333 | 13.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | LO | 90% | 100% | 0% | 0% | 0% |  | 1
25SRC001 | Back Grid | Back Grids | Central Sourcing | SRC | Central | III: Alternative Sourcing (Conditions or Security) | 0 | 0 | 0 | 0 | in BDG | Sep_25 | 2.9396 | 0.58791 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50% share - not started | MED | 60% | 0% | 0% | 0% | 0% |  | 2
25CPG007 | Doors OUTSOURCING (ROMANIA) PLUS/MAX | Assembled Door | Central Procurement | CPG | Central | II: Sourcing (Supply Extension or Re-Spec'ing) | 0 | 0 | 0 | 0 | in BDG | Mar_25 | 150 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | HI | 90% | 0% | 0% | 90% | 0% |  | 3
25IND001 | Aluminium Profiles : New Supplier Development MM Metacraft -> Jindal Al. | Aluminium Profiles | Central Procurement | IND | Central | III: Alternative Sourcing (Conditions or Security) | NO | n/a | NO | n/a | in BDG | Jan_25 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | HI | 80% | 100% | 0% | 0% | 0% |  | 3

## RPD Capacity
RPD Capacity (Spillover Projects and Projects Registered in 2026)
Country | Subgroup | Year | Area | Total Project Load Weeks (Process derived) | Total Project Load Weeks (Estimated) | 2026-Yearly Capacity | Gap | %age Completion w.r.t Total Projects | Remarks | [16 empty] | R&D and PD separate
India | PD | 2026 | Design Week | 794 |  | 252.6167 | 541.3833 | 31.82%
India | R&D | 2026 | Design Week | 38 |  | 87.8667 | -49.8667 | 231.2%
India | R&D | 2026 | Lab Week | 621.5 |  | 186.22 | 435.28 | 29.96%
Greece | R&D | 2026 | Design Week | 65 |  | 124.88 | -59.88 | 192.1%
Greece | R&D | 2026 | Lab Week | 65 |  | 72.96 | -7.96 | 112.2%
Romania | PD | 2026 | Design Week | 455 |  | 165 | 290 | 36.26%
Romania | PD | 2026 | Lab Week | 413 |  | 216.3 | 196.7 | 52.37%
Global Design Man Weeks/Lab Weeks Requirement Vs Available Capacity
|  | Project Request (MM/YY) | (All)
|  | Project to be considered for Capacity Calculation | Y
|  |  | No of Projects | Design |  | Testing |  |  | Safety
|  | Row Labels | Count of Project Category | Sum of Process Design Man Week | Sum of Actual Design Man Week | Count of Certification Testing Required | Sum of Lab Weeks- Process Derived | Sum of Actual Testing Time | Count of Safety Certification Required
|  | R&D-Greece | 5 | 65 |  | 4 | 4 | 18
|  | A | 1 | 20 |  | 1 |  | 1
|  | A+ | 1 | 30 |  | 1 | 4 | 8
|  | B | 2 | 10 |  | 2 |  | 9
|  | C | 1 | 5 |  |  |  | 0
|  | R&D-India | 2 | 38 | 167 | 2 | 88 | 99 | 1
|  | A | 2 | 38 | 167 | 2 | 88 | 99 | 1
|  | PD-India | 207 | 794 | 615.2 | 128 | 533.5 | 2553 | 70
|  | A | 1 | 19 | 19 | 1 | 6 | 6 | 1
|  | B | 146 | 587 | 451.5 | 109 | 496.5 | 2521 | 51
|  | C | 60 | 188 | 144.7 | 18 | 31 | 26 | 18
|  | PD-Romania | 24 | 455 | 413 | 20 | 994 | 1104 | 3
|  | B | 19 | 380 | 345 | 17 | 980 | 1054 | 3
|  | C | 5 | 75 | 68 | 3 | 14 | 50
|  | OEM-HCK | 12 | 60 |  | 1 |  | 4
|  | B-OEM | 12 | 60 |  | 1 |  | 4
|  | OEM-SEITEK | 12 | 118 |  |  |  | 0
|  | A-OEM | 3 | 70 |  |  |  | 0
|  | B-OEM | 9 | 48
Design Resource count & Design Capacity Calculation |  | Grand Total | 262 | 1530 | 1195.2 | 155 | 1619.5 | 3778 | 74
Resource Count | Global Design Resource Count | [6 empty] | India (PD) |  |  | India (R&D) |  |  | Greece (R&D) |  |  | Romania (PD)
|  | India PD | India R&D | Greece R&D | Romania PD | Global |  | Count of Design Engineer | 5.75 |  | Count of Design Engineer | 2 |  | Count of Design Engineer | 2.8 |  | Count of Design Engineer | 3.75
| No. of Resources | 5.75 | 2 | 2.8 | 3.75 | 14.3 |  | Engineer Name | Resource Count | Remarks | Engineer Name | Resource Count | Remarks | Engineer Name | Resource Count | Remarks | Engineer Name | Resource Count | Remarks
|  | 40.21% | 13.99% | 19.58% | 26.22% | 100% |  | Rishi | 1 |  | Ashish | 1 |  | Dimopoulou | 1 | R&D resource | Stef Marius | 1
[8 empty] | New Hiring | 0 | To be hired | Praveer Kumar Singh | 0.5 |  | Lioumis | 1 | R&D resource | Alin Boboc | 1
[8 empty] | Lokesh | 1 |  | Ayush Kumar | 0.5 | 3rd Party | Kanarios | 0.8 | Sourcing | Adrian Bortoc | 1
[8 empty] | Zakir | 1 | [7 empty] | Bianca | 0.75
[8 empty] | Pawan | 1
[8 empty] | Nikhil | 0.75
[8 empty] | Atul | 0.5
[8 empty] | Rahul-Contractual | 0.5 | 3rd Party
[8 empty] | New engineer-Contractual | 0 | 3rd Party
Global Design Capacity (Man Weeks) | Global Design Capacity (Man Weeks) | [6 empty] | India (PD) |  |  | India (R&D) |  |  | Greece (R&D) |  |  | Romania (PD)
|  | India (PD) | India (R&D) | Greece (R&D) | Romania (PD) | Global |  |  | Full Year | Yearly Remaining Capacity |  | Full Year | Yearly Remaining Capacity |  | Full Year | Yearly Remaining Capacity |  | Full Year | Yearly Remaining Capacity
| Total Yearly Capacity (Man Week) | 252.6167 | 87.8667 | 124.88 | 165 | 630.3633 |  | Total Design Capacity (Man Weeks) | 252.6167 | 179.7465 | Total Design Capacity (Man Weeks) | 87.8667 | 62.5205 | Total Design Capacity (Man Weeks) | 124.88 | 83.2569 | Total Design Capacity (Man Weeks) | 165 | 109.9038
| Remaining Capacity (Man Week) for Year 2026 | 179.7465 | 62.5205 | 83.2569 | 109.9038 | 435.4278 |  | Descrption | No. of Weeks | 0.71154 | Descrption | No. of Weeks | 0.71154 | Descrption | No. of Weeks | 0.67308 | Descrption | No. of Weeks | 0.67308
[8 empty] | Total Number Of Weeks | 52 | 37 | Total Number Of Weeks | 52 | 37 | Total Number Of Weeks | 52 | 35 | Total Number Of Weeks | 52 | 35
[8 empty] | National Holidays | 2.1667 | 1.5417 | National Holidays | 2.1667 | 1.5417 | National Holidays | 2.4 | 1.7077 | National Holidays | 2.6 | 1.85
[8 empty] | Medical Leave | 1.4 | 0.99615 | Medical Leave | 1.4 | 0.99615 | Medical Leave | 0 | 0 | Medical Leave | 1.4 | 0.99615
[8 empty] | Casual Leave | 1.1667 | 0.83013 | Casual Leave | 1.1667 | 0.83013 | Casual Leave | 0 | 0 | Casual Leave | 0 | 0
[8 empty] | Annual Leaves | 3.3333 | 2.3718 | Annual Leaves | 3.3333 | 2.3718 | Annual Leaves | 5 | 3.5577 | Annual Leaves | 4 | 2.8462
[8 empty] | Yearly Working Weeks/Per Engineer | 43.9333 | 31.2603 | Yearly Working Weeks/Per Engineer | 43.9333 | 31.2603 | Yearly Working Weeks/Per Engineer | 44.6 | 29.7346 | Yearly Working Weeks/Per Engineer | 44 | 29.3077
LAB →Chamber/Platform Count and Lab Week Capacity Calculation
Count for Lab Platform and Chamber | Global count of Lab Platform and Chamber | [6 empty] | India |  | Greece |  | Romania
|  | India | Greece | Romania | Total |  |  | Chamber Name | Platform Count | Chamber Name | Platform Count | Chamber Name | Platform Count
| No. of Chamber | 3 | 2 | 4 | 9 |  |  | CH-1 | 1 | CH-1 | 1 | CH-1 | 2
| No. of Test Paltform/Station | 8 | 3 | 8 | 19 |  |  | CH-2 | 4 | CH-2 | 2 | CH-2 | 2
|  | 42.11% | 15.79% | 42.11% |  |  |  | CH-3 | 2 |  |  | CH-3 | 2
[8 empty] | CH-4 | 1 |  |  | CH-4 | 2
[7 empty] | Total Chamber count/Platform Count | 4 | 8 | 2 | 3 | 4 | 8
Glabal Chamber Capacity (Lab weeks) | Global Chamber Capacity (Lab Weeks) | [6 empty] | India Per Chamber -Labweeks | [5 empty] | Greece Per Chamber -Labweeks | [5 empty] | Romania Per Chamber -Labweeks
|  | India | Greece | Romania | Total |  |  |  | Ch-1 | Ch-2 | Ch-3 | Ch-4 |  |  | Ch-1 | Ch-2 |  |  |  |  | Ch-1 | Ch-2 | Ch-3 | Ch-4
| Total Yearly Capacity (Lab Week) | 186.22 | 72.96 | 216.3 | 475.48 |  |  | Lab Weeks/Platform | 52 | 52 | 52 | 52 |  | Lab Weeks/Platform | 52 | 52 |  |  |  | Lab Weeks/Platform | 52 | 52 | 52 | 52
|  | 39.16% | 15.34% | 45.49% |  |  |  | National Holidays | 2.6 | 2.6 | 2.6 | 2.6 |  | National Holidays | 2.6 | 2.6 |  |  |  | National Holidays | 2.6 | 2.6 | 2.6 | 2.6
[8 empty] | Preventive Maintenance @quaterly once | 2 | 2 | 2 | 2 |  | Preventive Maintenance | 2 | 2 |  |  |  | Preventive Maintenance | 2 | 2 | 2 | 2
[8 empty] | Breakdown -Actual 2025 data | 1 | 11 | 7 | 2 |  | Breakdown | 8 | 8 |  |  |  | Breakdown | 3 | 3 | 3 | 4
| Remaining Capacity (Lab Week) | 132.5027 | 51.9138 | 153.9058 | 338.3223 |  |  | Calibration | 1 | 1 | 1 | 1 |  | Calibration | 1 | 1 |  |  |  | Calibration | 1 | 1 | 1 | 1
[8 empty] | Working Weeks/Chamber | 45.4 | 35.4 | 39.4 | 44.4 |  | Working Weeks/Chamber | 38.4 | 38.4 |  |  |  | Working Weeks/Chamber | 43.4 | 43.4 | 43.4 | 42.4
[8 empty] | Weekdays | 6 |  |  |  |  | Weekdays | 5 |  |  |  |  | Weekdays | 5
[8 empty] | India total Lab Weeks | [5 empty] | Greece total Lab Weeks | [5 empty] | Romania total Lab Weeks
[8 empty] | Chamber Name | Platform Count | Effciency | Total Lab Weeks/Platform | Efficient Lab Weeks | Remarks | Chamber Name | Platform Count | Effciency | Total Lab Weeks/Platform | Efficient Lab Weeks | Remarks | Chamber Name | Platform Count | Effciency | Total Lab Weeks/Platform | Efficient Lab Weeks | Remarks
[8 empty] | CH-1 | 1 | 70% | 31.78 | 31.78 |  | CH-1 | 1 | 70% | 26.88 | 26.88 |  | CH-1 | 1 | 70% | 30.38 | 30.38
[8 empty] | CH-2 | 4 | 60% | 21.24 | 84.96 | Multiple platform so efficiency is low not all platform can be run | CH-2 | 2 | 60% | 23.04 | 46.08 |  | CH-2 | 4 | 60% | 26.04 | 104.16 | Multiple platform so efficiency is low not all platform can be run
[8 empty] | CH-3 | 2 | 60% | 23.64 | 47.28 | Multiple platform so efficiency is low not all platform can be run | [6 empty] | CH-3 | 2 | 60% | 26.04 | 52.08 | Multiple platform so efficiency is low not all platform can be run
[8 empty] | CH-4 | 1 | 50% | 22.2 | 22.2 | [7 empty] | CH-4 | 1 | 70% | 29.68 | 29.68
[8 empty] | 4 | 8 |  | Total | 186.22 | Old labs/Chamber 4 only use for reliability | 2 | 3 |  | Total | 72.96 |  | 4 | 8 |  | Total | 216.3 | New Labs
[11 empty] | Reamining Year Capacity | 132.5027 |  |  |  |  | Reamining Year Capacity | 51.9138 |  |  |  |  | Reamining Year Capacity | 153.9058
71.15%
Note on K55: Gahlot Sachin: Calculation for Remaining Week
Note on N55: Gahlot Sachin: Calculation for Remaining Week
Note on J69: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Only For Industrialization-Non Calibrated Lab

## Final RPD
Development Process Steps | PD RoadMap Steps --> | PDD-A | PDD-B | PDD-C | PDD-D | PDD-E | PDD-F | PDD-G | PDD-H | PDD-I | PDD-J | PDD-K | PDD-L | PDD-M | PDD-N
|  | Marketing Brief | Feasibility Study (Conceptual Design) | Business case Approval | Final Technical Brief & Project Kick Off | Design Detailing | Proof of Concept | Online CAPEX approval | Certification testings & Complaince | TF -1 | Pr. Pr | TF -2 | Pilot | TF-3 | Commercialization
| Project Category | PDD-A: Lead Times (wks) per Phase | Sum | Design Time- Project leader concept | Lab Time | Safety Time
| A+ | 1 | 8 | 4 | 1 | 6 | 6 | 2 | 6 | 2 | 1 | 2 | 3 | 1 | 1 | 44 | 22 | 12
| A | 1 | 4 | 4 | 1 | 6 | 4 | 2 | 6 | 2 | 1 | 2 | 3 | 1 | 1 | 38 | 18 | 10
| B | 1 | 0 | 0 | 1 | 4 |  | 0 | 6 |  | 1 | 2 | 1 | 1 | 1 | 18 | 8 | 6
| C | 1 | 0 | 0 | 1 | 2 |  | 0 | 1 |  | 1 | 1 | 0 | 0 | 1 | 8 | 4 | 1
| OEM Development Steps --> | OEM-A | OEM-B | OEM-C | OEM-D | OEM-E | OEM-F | OEM-G | OEM-H | OEM-I | OEM-J | OEM-K | OEM-L | OEM-M | OEM-N
|  | Commercial Brief | Final Technical Brief & Project Kick Off | Business case Approval | Design Detailing | Proof of Concept | Online CAPEX approval | Test results analysis | Certification testings & Complaince | TF -1 | Pr. Pr | TF -2 | Pilot | TF-3 | Commercialization
| Project Category | OEM-A: Lead Times (wks) per Phase (only for Frigoglass Resources)
| A-OEM | 1 | 1 | 1 | 2 | 2 | 2 | 4 | 6 | 0 | 1 | 0 | 0 | 0 | 1 | 21
| B-OEM | 1 | 1 | 1 | 0 | 0 | 2 | 2 | 6 | 0 | 1 | 0 | 0 | 0 | 0 | 14
| C-OEM | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 4
Steps are done by OEM
Global RPD → Conversion Factor, Resource Count, Capacity Required & Available Capacity for Design and Testing
Color Coding | bar: OEM-A to OEM-E
| Design | OEM-A: Testing; OEM-B: Global; OEM-C: India; OEM-D: Greece; OEM-E: Romania
Conversion Factor | Conversion Factor for Process Driven DesignTimeline | OEM-F: Conversion Factor for Process Driven Testing Timeline
| Catogory of Projects | OEM-A: Design Man Weeks/Project (Made considering only design time); OEM-B: %age; OEM-C: Conversion Factor (B considered as 1); OEM-D: For Project leader concept (Man week required) as per Process Defined above; OEM-F: Catogory of Projects; OEM-G: Lab Weeks/Project; OEM-H: %age; OEM-I: Conversion Factor (B considered as 1)
| A+ | OEM-A: 19; OEM-B: 475%; OEM-C: 4.75; OEM-D: 22; OEM-F: A+; OEM-G: 16; OEM-H: 160%; OEM-I: 1.6
| A | OEM-A: 15; OEM-B: 375%; OEM-C: 3.75; OEM-D: 18; OEM-F: A; OEM-G: 14; OEM-H: 140%; OEM-I: 1.4
| B | OEM-A: 4; OEM-B: 100%; OEM-C: 1; OEM-D: 8; OEM-F: B; OEM-G: 10; OEM-H: 100%; OEM-I: 1
| C | OEM-A: 3; OEM-B: 75%; OEM-C: 0.75; OEM-D: 4; OEM-F: C; OEM-G: 2; OEM-H: 20%; OEM-I: 0.2
| A-OEM | OEM-A: 4; OEM-B: 100%; OEM-C: 1; OEM-F: A-OEM; OEM-G: 6; OEM-H: 60%; OEM-I: 0.6
| B-OEM | OEM-A: 1; OEM-B: 25%; OEM-C: 0.25; OEM-F: B-OEM; OEM-G: 6; OEM-H: 60%; OEM-I: 0.6
| C-OEM | OEM-A: 0.5; OEM-B: 12.5%; OEM-C: 0.125; OEM-F: C-OEM; OEM-G: 2; OEM-H: 20%; OEM-I: 0.2
'2024-25-26 Projects'!$A$5:$AI$550

## Lists & Explanations
Project Initiation | Source | Plant | Requesting Department | Project Category | Project Status | Functional Group | RM Category | Component Group | Project Type | Means | Development Step | Development Step Description | Priority | General Status | RPD HUB | Product Type | Resource Name | Safety Certification Required | Safety Certification Status | Testing Required | Marketing Brief | HO review status | Custiomer
2024-01-01 | FRG | IND | PD | A+ | In Que | Insulated Cabin | Al. Sheets | Steel & Parts | NM | New Model | Not Started | N/A | 1 | Not Started | R&D-India | ICM | Sachin | Yes | Not Started | POC | Yes | Development | ALL
2024-02-01 | OEM | INN | Marketing/Sales | A | In Progress | Cooling Mechanism | Aluminium Profiles | Door Components & Acc. | NO | New Options | PDD-A | MKTG_BRF | 2 | On Time | R&D-Greece | HA | Ritu | No | In Progress | Performance | No | Industrialization | COKE
2024-03-01 |  | Multiplant | Quality | B | Delayed | Door | Assembled Door | Door Components & Acc. | CO | Cost optimization | PDD-B | FEAS_STD | 3 | Delayed | PD-India | VF | Kamal |  | Delayed | Energy | NA | In Que | KA
2024-04-01 |  | ROM | Service | C | Completed | Cabin Electronics | Asset Tags | Other | IMP | Improvement | PDD-C | BUS_CASE | 4 | Completed | PD-Romania | CF | Rahul |  | Completed | Comparision |  | On Hold | WM
2024-05-01 |  | SAF | Central Procurement Group | A-OEM | Cancelled | Electrical Parts | Back Grids | Steel & Parts | AC | Alternative Component | PDD-D | TECH_BRIEF | 5 | Failed | OEM-HCK | Other | Zakir |  | Hold | Reliability |  | Commercialized
2024-06-01 |  | OEM-HCK | Central Supply Chain | B-OEM | On hold | Shelving | Ballast | Electrical Components | SER | Service | PDD-E | DESIGN | 6 | Cancelled | OEM-SEITEK |  | Lokesh |  | N/A |  |  | Cancelled
2024-07-01 |  | OEM-Seitek | Local Supply Chain | C-OEM |  | Packaging | Block Motors | Electrical Components | CER | Customer (re-) Certification | PDD-F | POC | 7 |  |  |  | Pawan
2024-08-01 |  | Egypt | Central R&PD |  |  | Other Fastening | Brazing materials | Cooling Components | BC | Business Continuity | PDD-G | CAPEX | 8 |  |  |  | Ashish
2024-09-01 |  | OEM-VEELINE | Local R&PD |  |  | Illumination | Cable Harnesses | Electrical Components | OEM | OEM | PDD-H | CERT | 9 |  |  |  | Theoni
2024-10-01 |  | OEM-NEW STAR | Central Quality |  |  | Artwork | Carton box | Packaging | RPD Support |  | PDD-I | TF_1 | 10 |  |  |  | Antonis
2024-11-01 |  |  | Local Quality |  |  | Complete Cooler | Compressor Accessories | Cooling Components |  |  | PDD-J | PROD_PR | 11 |  |  |  | Marian
2024-12-01 |  |  | CR&PD & CPG |  |  |  | Compressors | Cooling Components |  |  | PDD-K | TF_2 | 12 |  |  |  | Alin
2025-01-01 | [6 empty] | Copper Components | Cooling Components |  |  | PDD-L | PILOT | 13 |  |  |  | Catalin
2025-02-01 | [6 empty] | Copper Tubes | Cooling Components |  |  | PDD-M | TF_3 | 14 |  |  |  | Adrian
2025-03-01 | [6 empty] | Cross Flow Motors | Electrical Components |  |  | PDD-N | COMM | 15 |  |  |  | Stef
2025-04-01 | [6 empty] | EPS | Packaging |  |  | Not Started | N/A | 16 |  |  |  | Rishi
2025-05-01 | [6 empty] | Electrical Components | Electrical Components |  |  | OEM-A | COMM_BRF | 17 |  |  |  | Pawan
2025-06-01 | [6 empty] | Electronic Controllers & Acces | Electrical Components |  |  | OEM-B | TECH_BRIEF | 18 |  |  |  | Nikhil
2025-07-01 | [6 empty] | Electronic Motors | Electrical Components |  |  | OEM-C | BUS_CASE | 19 |  |  |  | Sailesh
2025-08-01 | [6 empty] | Extrusion pl. Profiles | Plastics |  |  | OEM-D | DESIGN | 20 |  |  |  | Atul
2025-09-01 | [6 empty] | Fastening Materials | Other |  |  | OEM-E | POC | 21 |  |  |  | Elena Micu
2025-10-01 | [6 empty] | Fluorescent Tubes | Electrical Components |  |  | OEM-F | CAPEX | 22 |  |  |  | Bianca
2025-11-01 | [6 empty] | Glass | Door Components & Acc. |  |  | OEM-G | TST_ANAL | 23 |  |  |  | Dipak
2025-12-01 | [6 empty] | HEX | Cooling Components |  |  | OEM-H | CERT | 24
2026-01-01 | [6 empty] | Injection Plastics | Plastics |  |  | OEM-I | TF_1 | 25
2026-02-01 | [6 empty] | LED | Electrical Components |  |  | OEM-J | PROD_PR | 26
2026-03-01 | [6 empty] | Labels & Manuals | Other |  |  | OEM-K | TF_2 | 27
2026-04-01 | [6 empty] | Locks | Electrical Components |  |  | OEM-L | PILOT | 28
2026-05-01 | [6 empty] | Magnetic Gaskets | Door Components & Acc. |  |  | OEM-M | TF_3 | 29
2026-06-01 | [6 empty] | Metal Processing & Components | Steel & Parts |  |  | OEM-N | COMM | 30
2026-07-01 | [6 empty] | Night Blinds | Steel & Parts |  |  |  | Certification- In progress | 31
2026-08-01 | [6 empty] | Other Materials | Other |  |  |  | POC- In progress | 32
2026-09-01 | [6 empty] | PSU | Electrical Components |  |  |  | Safety - In progress | 33
2026-10-01 | [6 empty] | Plastic Sheets | Plastics |  |  |  | 1 | 34
2026-11-01 | [6 empty] | Plastic bags & Stretch Film | Packaging |  |  |  |  | 35
2026-12-01 | [6 empty] | Polyurethane Materials | Plastics |  |  |  |  | 36
[7 empty] | Powders | Plastics |  |  |  |  | 37
[7 empty] | Power Cables | Electrical Components |  |  |  |  | 38
[7 empty] | Printing Materials | Other |  |  |  |  | 39
[7 empty] | Refrigerants | Cooling Components |  |  |  |  | 40
[7 empty] | Shaded Pole Motors & Blades | Electrical Components |  |  |  |  | 41
[7 empty] | Shelves | Shelves |  |  |  |  | 42
[7 empty] | Silicones | Other |  |  |  |  | 43
[7 empty] | Silk Screened Parts | Other |  |  |  |  | 44
[7 empty] | Steel-GI | Steel & Parts |  |  |  |  | 45
[7 empty] | Steel-PPGI | Steel & Parts |  |  |  |  | 46
[7 empty] | Tapes&Other Packaging Material | Packaging |  |  |  |  | 47
[7 empty] | Thermostats | Electrical Components |  |  |  |  | 48
[7 empty] | WOT | Cooling Components |  |  |  |  | 49
[7 empty] | Wooden Pallets | Packaging |  |  |  |  | 50
[7 empty] | Compressors & Accessories | Cooling Components |  |  |  |  | 51
[7 empty] | Protector - Stabilizer | Electrical Components |  |  |  |  | 52
[7 empty] | Shelves & Back Grids | Shelves |  |  |  |  | 53
[7 empty] | Thermoformed Parts | Plastics |  |  |  |  | 54
[7 empty] | HONEYCOMB | Packaging |  |  |  |  | 55
[7 empty] | N/A | N/A

## Delete (hidden)
RPDO hub | PD-Romania
Count of Project Status | Column Labels
Row Labels | A | B | C | Grand Total
Development |  | 6 | 6 | 12
In Que |  | 4 | 3 | 7
Industrialization | 1 | 14 | 2 | 17
On Hold |  | 13 | 6 | 19
Grand Total | 1 | 37 | 17 | 55
[5 empty] | Row Labels | A | B | C | Grand Total
[5 empty] | Development |  | 6 | 7 | 13
[5 empty] | In Que |  | 5 | 2 | 7
[5 empty] | Industrialization | 4 | 3 | 2 | 9
[5 empty] | On Hold |  | 9 | 3 | 12
[5 empty] | Grand Total | 4 | 23 | 14 | 41

## 2026 Project-Delete (hidden)
Cost Saving | Business Continiuty | New Model | Improvement | New Option | Service | [13 empty] | Certification testings & Complaince | TF -1 | Pr. Pr | TF -2 | Pilot | TF-3 | Commercialization
2026 RPD Project Pipeline Charter | [18 empty] | Mar | Mar | Mar | Mar | Mar | Apr | Apr | Apr | Apr | Jun | Jun | Jun | Jun | Jul | Jul | Jul | Jul | Aug/Creo traianing | Aug | Aug | Aug | Sep | Sep | Sep | Sep | Sep | Oct | Oct | Oct | Oct | Nov | Nov | Nov | Nov | Dec | Dec | Dec | Dec
No. | Project Request (MM/YY) | Project Category | Project Type | Online PD Database Project Code | Project Name | Status (Spill over/New) | Plant/OEM | RPDO hub | Product Type | Requesting Department | Customer | Status/2025/2026 Spillover | Project Status | Project Review Remarks | Project Leader | Project End Date - LATEST | Part of "IMPACT" | Marketing Brief Yes/NO | wk10 | wk11 | wk12 | wk13 | wk14 | wk15 | wk16 | wk17 | wk18 | wk24 | wk25 | wk26 | wk27 | wk28 | wk29 | wk30 | wk31 | wk32 | wk33 | wk34 | wk35 | wk36 | wk37 | wk38 | wk39 | wk40 | wk41 | wk42 | wk43 | wk44 | wk45 | wk46 | wk47 | wk48 | wk49 | wk50 | wk51 | wk52
1 | 2026-01-01 | A | NM | TBR | BoB model double HD & SD door - C condition in house production - Key accounts | New | IND | PD-India | ICM | Marketing/Sales | All |  | In Que
2 | 2026-01-01 | B | BC | TBR | S-500 development as per EC-26 protocol - COKE | New | IND | PD-India | ICM | Marketing/Sales | Coke |  | In Que
3 | 2026-01-01 | A | NM | TBR | 50L countertop development form OEM - Key accounts & Coke - in house production | New | IND | PD-India | Other | Marketing/Sales | WM |  | In Que
4 | 2026-01-01 | B | NO | TBR | Frameless look alike aesthetics for India models | New | IND | PD-India | ICM | Marketing/Sales | All |  | In Que
5 | 2026-01-01 | B | BC | 25-00308 | SFC-1000→ New Step Cabin design/Phase -2 | Spill Over | IND | PD-India | ICM | Marketing/Sales | All | C-2025 | In Que
6 | 2025-06-01 | B | BC | 24-00218 | VG 200 R290 - 5 star (All models in cabin) | Spill Over | IND | PD-India | ICM | Marketing/Sales | WM |  | In Que
7 | 2025-06-01 | B | BC | 24-00220 | VG 250 R290 - 5 star (All models in cabin) | Spill Over | IND | PD-India | ICM | Marketing/Sales | WM |  | In Que
8 | 2025-06-01 | B | BC | 24-00208 | VG 400 R290 - 5 star (All models in cabin) | Spill Over | IND | PD-India | ICM | Marketing/Sales | WM |  | In Que
9 | 2025-06-01 | B | BC | 24-00209 | VG 300 R290 - 5 star (All models in cabin) | Spill Over | IND | PD-India | ICM | Marketing/Sales | WM |  | In Que
10 | 2025-06-01 | B | BC | 24-00210 | VG 450 R290 - 5 star (All models in cabin) | Spill Over | IND | PD-India | ICM | Marketing/Sales | WM |  | In Que
11 | 2025-06-01 | B | BC | 24-00213 | VG500 R290 - 5 star (All models in cabin) | Spill Over | IND | PD-India | ICM | Marketing/Sales | WM |  | In Que
12 | 2025-06-01 | B | BC | 24-00216 | VG 550 R290 - 5 star (All models in cabin) | Spill Over | IND | PD-India | ICM | Marketing/Sales | WM |  | In Que
13 | 2025-06-01 | B | BC | 24-00211 | VG600 R290 - 5 star (All models in cabin) | Spill Over | IND | PD-India | ICM | Marketing/Sales | WM |  | In Que
14 | 2025-06-01 | B | BC | 24-00217 | VG 650 R290 - 5 star (All models in cabin) | Spill Over | IND | PD-India | ICM | Marketing/Sales | WM |  | In Que
15 | 2025-06-01 | B | BC | 24-00215 | VG700 R290 - 5 star (All models in cabin) | Spill Over | IND | PD-India | ICM | Marketing/Sales | WM |  | In Que
16 | 2025-06-01 | B | BC | 24-00214 | VG950 R290 - 5 star (All models in cabin) | Spill Over | IND | PD-India | ICM | Marketing/Sales | WM |  | In Que
17 | 2025-06-01 | B | BC | 24-00219 | VG 1100 R290 - 5 star (All models in cabin) | Spill Over | IND | PD-India | ICM | Marketing/Sales | WM |  | In Que
18 | 2026-01-01 | B | NM | TBR | SP 200 development as per META - Pepsi certification only | New | IND | PD-India | ICM | Marketing/Sales | Pepsico |  | In Que
19 | 2026-01-01 | B | BC | TBR | S-45 testing and development - As per Heineiken protocol | New | IND | PD-India | ICM | Marketing/Sales | KA |  | In Que
20 | 2026-01-01 | B | BC | TBR | S-60 testing and development - As per Heineiken protocol | New | IND | PD-India | ICM | Marketing/Sales | KA |  | In Que
21 | 2026-01-01 | B | BC | TBR | S-1100 testing and development - As per Heineiken protocol | New | IND | PD-India | ICM | Marketing/Sales | KA |  | In Que
22 | 2026-01-01 | B | BC | TBR | S-45 SZ for Heineken for HEINEKEN - Feasibility to define cost & CAPEX for EEI<15 & EEI<20 | New | SAF | PD-India | ICM | Marketing/Sales | KA |  | In Que
23 | 2026-01-01 | B | BC | TBR | S-60 SZ for Heineken for HEINEKEN - Feasibility to define cost & CAPEX for EEI<15 & EEI<20 | New | SAF | PD-India | ICM | Marketing/Sales | KA |  | In Que
24 | 2026-01-01 | B | CO | TBR | PSU Done 8W/15-16W/24W/30W as alternative to Tauras | Spill Over | Multiplant | PD-India | ICM | Marketing/Sales | All |  | In Que
25 | 2026-01-01 | A | BC | TBR | FV-1000 SZ for Heineken - Feasibility to define cost & CAPEX for EEI<15 & EEI<20 | New | SAF | PD-India | ICM | Marketing/Sales | KA |  | In Que
26 | 2025-01-01 | B | NM | 25-00327 | SC-300 R290 conversions with cost effective measures - BSL | Spill Over | IND | PD-India | ICM | Marketing/Sales | KA |  | In Que
27 | 2025-01-01 | B | NM | 25-00328 | SC-375 R290 conversions with cost effective measures - BSL | Spill Over | IND | PD-India | ICM | Marketing/Sales | KA |  | In Que
28 | 2025-01-01 | B | NM | 25-00329 | SC-500 R290 conversions with cost effective measures - BSL | Spill Over | IND | PD-India | ICM | Marketing/Sales | KA |  | In Que
29 | 2025-01-01 | B | NM | 25-00330 | SC-650 R290 conversions with cost effective measures - BSL | Spill Over | IND | PD-India | ICM | Marketing/Sales | KA |  | In Que
30 | 2025-01-01 | B | NM | 25-00331 | SC-1000 R290 conversions with cost effective measures - BSL | Spill Over | IND | PD-India | ICM | Marketing/Sales | KA |  | In Que
31 | 2026-01-01 | C | NO | TBR | Aesthetical upgrade (icool2 doors with Neon LED or Strip) in key account models - S. African range (S-45 SZ) - Key accounts | New | SAF | PD-India | ICM | Marketing/Sales | KA |  | In Que
32 | 2026-01-01 | C | NO | TBR | Aesthetical upgrade (icool2 doors with Neon LED or Strip) in key account models - S. African range ( SL640) - Key accounts | New | SAF | PD-India | ICM | Marketing/Sales | KA |  | In Que
33 | 2026-01-01 | C | NO | TBR | Aesthetical upgrade (icool2 doors with Neon LED or Strip) in key account models - S. African range (HV-71) - Key accounts | New | SAF | PD-India | ICM | Marketing/Sales | KA |  | In Que
34 | 2026-01-01 | C | NO | TBR | Aesthetical upgrade (icool2 doors with Neon LED or Strip) in key account models - S. African range (FV-1000) - Key accounts | New | SAF | PD-India | ICM | Marketing/Sales | KA |  | In Que
35 | 2026-01-01 | C | NO | TBR | Aesthetical upgrade (icool2 doors with Neon LED or Strip) in key account models - S. African range (FV 1000 SZ) - Key accounts | New | SAF | PD-India | ICM | Marketing/Sales | KA |  | In Que
37 | 2026-01-01 | C | SER | TBR | HV-71 safe cooler development | Spill Over | SAF | PD-India | ICM | Marketing/Sales | Coke |  | In Que
38 | 2026-01-01 | B | CO | TBR | S-250 as per EC26 protocol | Spill Over | IND | PD-India | ICM | Marketing/Sales | Coke |  | In Que
39 | 2026-01-01 | A | NM | TBR | 350L premium slim cooler development, New platform project - Indonesia Pepsi | Spill Over | INN | PD-India | ICM | Marketing/Sales | Pepsico |  | In Que
40 | 2026-01-01 | A | CO | TBR | 9 facing single door HC @ 60HZ & D-Condition with back airflow and market required features (HD Shelves, SS based, Temp. display castor. Etc) that is based on existing cabin – Meet CC EC26 requirement | New | IND | PD-India | ICM | Marketing/Sales | Coke |  | In Que
41 | 2026-01-01 | B | BC | TBR | FV-1000 D development as per Coke EC 26 | Spill Over | INN | PD-India | ICM | Marketing/Sales | Coke |  | In Que
42 | 2026-01-01 | B | BC | TBR | E-47 development as per EC-26 protocol - CPNG | Spill Over | INN | PD-India | ICM | Marketing/Sales | Coke |  | In Que
43 | 2024-12-01 | C | CO | 22-00060 | ON OFF switch development | Spill Over | IND | PD-India | ICM | Central Procurement Group | ALl |  | In Que
44 | 2024-08-01 | C | CO | 24-00226 | Huawei PSUs | Spill Over | Multiplant | PD-India | ICM | Central Procurement Group | All |  | In Que
45 | 2025-02-01 | C | CO | 25-00249 | Sedes Heaters for India and South Africa | Spill Over | Multiplant | PD-India | ICM | Central Procurement Group | All |  | In Que
46 | 2025-06-01 | C | CO | 25-00353 | Alternative Shaded Pole 7W Xing Yuang YZF 7-20 ALUMINIUM WIRE for Hicool 83A230SAC-7W | Spill Over | Multiplant | PD-India | ICM | Central Procurement Group | All |  | In Que
47 | 2025-06-01 | C | CO | 25-00354 | Alternative Shaded Pole 5W Xing Yuang YZF 7-20 for Hicool 83A230SAC-7W | Spill Over | Multiplant | PD-India | ICM | Central Procurement Group | All |  | In Que
48 | 2024-08-06 08:08 | C | CO | 24-00223 | Jinbo PSUs | Spill Over | Multiplant | PD-India | ICM | Central Procurement Group | All |  | In Que
49 | 2025-06-26 06:55 | C | CO | 25-00347 | Alternative AC Block Motor CCA WIRE Xing Yuang 20W (FM12038A2HS) for Nisiki NIS12038HS2W-ES | Spill Over | Multiplant | PD-India | ICM | Central Procurement Group | All |  | In Que
50 | 2025-06-26 06:56 | C | CO | 25-00348 | Alternative AC Block Motor Xing Yuang 20W (FM12038A2HS) for Nisiki NIS12038HS2W-ES | Spill Over | Multiplant | PD-India | ICM | Central Procurement Group | All |  | In Que
51 | 2025-06-26 06:58 | C | CO | 25-00351 | Alternative Shaded Pole 5W Xing Yuang YZF 5-13 ALUMINIUM WIRE for Hicool 83A230SAC-5W | Spill Over | Multiplant | PD-India | ICM | Central Procurement Group | All |  | In Que
52 | 2025-06-26 06:59 | C | CO | 25-00352 | Alternative Shaded Pole 5W Xing Yuang YZF 5-13 COPPER WIRE for Hicool 83A230SAC-5W | Spill Over | Multiplant | PD-India | ICM | Central Procurement Group | All |  | In Que
53 | 2025-06-26 07:03 | C | CO | 25-00357 | Alternative Shaded Pole 16W Xing Yuang YZF 16-25 ALUMINIUM WIRE for Weiguang YZF16-25 | Spill Over | Multiplant | PD-India | ICM | Central Procurement Group | All |  | In Que
54 | 2025-04-01 | B | IMP | TBR | Super-45 Design data synchronization with production (Product file) | Spill Over | IND | PD-India | ICM | PD | All |  | In Que
55 | 2025-04-01 | B | IMP | TBR | Super-60 Design data synchronization with production (Product file) | Spill Over | IND | PD-India | ICM | PD | All |  | In Que
56 | 2025-04-01 | B | IMP | TBR | Super-1100 Design data synchronization with production (Product file) | Spill Over | IND | PD-India | ICM | PD | All |  | In Que
57 | 2025-06-01 | B | NM | 25-00289-1 | S-60 R290 EG (PepsiCO & Generic customer) | Spill Over | Egypt | PD-India | ICM | Marketing/Sales | KA |  | In Que
58 | 2025-06-01 | B | NM | 25-00292-1 | S-1100 R290 EG (PepsiCO & Generic customer) | Spill Over | Egypt | PD-India | ICM | Marketing/Sales | KA |  | In Que
59 | 2025-12-01 | B | IMP | TBR | SM Updates-6 Nos. of SM | New | IND | PD-India | Other | PD | All |  | In Que
60 | 2024-08-01 | B | NO | 24-00523 | Plus-450 Vending cooler / Max-750 | Spill Over | ROM | PD-Romania | ICM | Marketing/Sales |  |  | Development
61 | 2025-08-01 | B | NO | 25-00628 | Max 750 Sub Zero | New | ROM | PD-Romania | ICM | Marketing/Sales |  |  | In Que
62 | 2025-11-01 | B | NO | 25-00640 | K2 controller settings for MAX B range & PoC for EEI<15 | New | ROM | PD-Romania | ICM | Marketing/Sales |  |  | Development
63 | 2025-10-01 | C | NO | 25-00639 | Development of Plus 1200 DD with FDE-32 (K4) | New | ROM | PD-Romania | ICM | Marketing/Sales |  |  | In Que
64 | 2025-08-01 | B | NO | 25-00629 | Sample 3D Branding ''Effect'' in Max 450 B | New | ROM | PD-Romania | ICM | Marketing/Sales |  |  | In Que
65 | 2025-07-01 | A | NM | 25-00621 | MAX-1200 HD A Rating for non-Coke | Spill Over | ROM | PD-Romania | ICM | Marketing/Sales |  |  | Industrialization
66 | 2025-02-10 | C | CO | 25-00586 | iPixel LEDs as alternative to Refond | Spill Over | ROM | PD-Romania | ICM | Central Procurement Group |  |  | On Hold
67 | 2025-02-10 | B | CO | 25-00589 | Saiwei 5W EC compact motor | Spill Over | ROM | PD-Romania | ICM | Central Procurement Group |  |  | On Hold
68 | 2025-02-10 | B | CO | 25-00591 | Honker controller | Spill Over | ROM | PD-Romania | ICM | Central Procurement Group |  |  | On Hold
69 | 2024-09-01 | B | CO | 24-00557 | PSU Done 24W | Spill Over | ROM | PD-Romania | ICM | Central Procurement Group |  |  | On Hold
70 | 2024-09-01 | B | CO | 24-00556 | PSU Done 16W | Spill Over | ROM | PD-Romania | ICM | Central Procurement Group |  |  | On Hold
71 | 2024-09-01 | B | CO | 24-00555 | PSU Done 12W | Spill Over | ROM | PD-Romania | ICM | Central Procurement Group |  |  | On Hold
72 | 2024-12-01 | C | NO | 24-00564 | New Coca-Cola branding for CCEP Europe | Spill Over | ROM | PD-Romania | ICM | Marketing/Sales |  |  | On Hold
73 | 2025-04-01 | C | NO | 25-00612 | Stabilization/Support kit for Plus 900 HD to prevent sagging of cooling mechanism due to customer mis-use | Spill Over | ROM | PD-Romania | ICM | Marketing/Sales |  |  | On Hold
74 | 2024-12-01 | B | NO | 24-00551 | Max 450 C Donper SK43CU1 Su 50 DU1 | Spill Over | ROM | PD-Romania | ICM | Central Procurement Group |  |  | On Hold
75 | 2024-12-01 | B | CO | 25-00590 | Keepthink controller | Spill Over | ROM | PD-Romania | ICM | Central Procurement Group |  |  | On Hold
76 | 2024-09-01 | B | CO | 24-00551 | Alternative compressor to Wanbao FTA45L - GMCC PA50EME | Spill Over | ROM | PD-Romania | ICM | Central Procurement Group |  |  | Development
77 | 2024-09-01 | B | CO | 24-00553 | Huaiy NUM90RAa | Spill Over | ROM | PD-Romania | ICM | Central Procurement Group |  |  | On Hold
78 | 2024-09-01 | B | CO | 24-00552 | Huaiy NFG80Ra | Spill Over | ROM | PD-Romania | ICM | Central Procurement Group |  |  | On Hold
79 |  | A | NM | TBR | MAX-1200 [R290] Freezer | Spill Over | ROM | R&D-Greece | VF | Marketing/Sales |  |  | In Que |  | Antonis
80 |  | B | NM | TBR | MAX-1200 [R290] Super Market Version | Spill Over | ROM | R&D-Greece | ICM | Marketing/Sales |  |  | In Que |  | Antonis
81 |  | A | NM | TBR | MAX-750 [R290] Freezer | Spill Over | ROM | R&D-Greece | VF | Marketing/Sales |  |  | In Que |  | Theoni
82 |  | B | NM | TBR | MAX-750 [R290] Super Market Version | Spill Over | ROM | R&D-Greece | ICM | Marketing/Sales |  |  | In Que |  | Theoni
83 |  | A | NM | TBR | MAX-750 Vending-Shekel | Spill Over | ROM | R&D-Greece | ICM | Marketing/Sales |  |  | Development |  | Theoni
84 |  | A | NM | TBR | MAX-750 Vending-NU | Spill Over | ROM | R&D-Greece | ICM | Marketing/Sales |  |  | Development |  | Theoni
85 |  | A | NM | TBR | NGC-450 - Double Bubble | Spill Over | ROM | R&D-Greece | ICM | Marketing/Sales |  |  | In Que
86 |  | B | NM | TBR | 8 facing FFD C rarting for EU (S-500 ex India) | Spill Over | ROM | R&D-Greece | ICM | Marketing/Sales |  |  | In Que
87 |  | A | NO | TBR | MAX/Plus 900 door design with French sealing solution (applied to household coolers) | New | ROM | R&D-Greece | ICM | Marketing/Sales |  |  | In Que
88 |  | B | NO | TBR | NGC-450 new door designs for Key accounts - 2 door designs | New | ROM | R&D-Greece | ICM | Marketing/Sales |  |  | In Que
89 |  | B | NO | TBR | 3D Beat BOX logo on ICOOL2 door of MAX-450 | New | ROM | R&D-Greece | ICM | Marketing/Sales |  |  | In Que
90 |  | B | NO | TBR | Provision for big 3D logo on MAX-750 | New | ROM | R&D-Greece | ICM | Marketing/Sales |  |  | In Que
91 |  | B | NO | TBR | ICOOL 2 door with Strip or LED on MAX 750 & MAX 1200 | New | ROM | R&D-Greece | ICM | Marketing/Sales |  |  | In Que
92 |  | A | NO | TBR | Door for Vending kit with integrated screen and POS | New | ROM | R&D-Greece | ICM | Marketing/Sales |  |  | In Que
93 |  | B | NO | TBR | Maxerience Max-750 Vending cooler | New | ROM | PD-Romania | ICM | Marketing/Sales |  |  | Development
94 |  | A | NM | TBR | MAX-1200 [R290] Freezer | New | ROM | R&D-Greece | VF | Marketing/Sales |  |  | In Que |  | Antonis
95 |  | C | NM | TBR | MAX-1200 [R290] Super Market Version | Spill Over | ROM | R&D-Greece | ICM | Marketing/Sales |  |  | In Que |  | Antonis
96 |  | B | NM | TBR | MAX-750 [R290] Freezer | Spill Over | ROM | R&D-Greece | VF | Marketing/Sales |  |  | In Que |  | Theoni
97 |  | C | NM | TBR | MAX-750 [R290] Super Market Version | Spill Over | ROM | R&D-Greece | ICM | Marketing/Sales |  |  | In Que |  | Theoni
98 | 2024-10-01 | B | NM | TBR | MAX-750 Vending-Shekel | Spill Over | ROM | R&D-Greece | ICM | Marketing/Sales |  |  | Development |  | Theoni
99 | 45962 | A-OEM | NM | TBR | Family Fridge | Spill Over | OEM-Seitek | OEM-SEITEK | ICM | Marketing/Sales |  |  | Development |  | Theoni
100 | 45962 | B-OEM | NO | TBR | IC2-40 ECO with FDE32 | Spill Over | OEM-Seitek | OEM-SEITEK | ICM | Marketing/Sales |  |  | Development |  | Theoni
101 | 45962 | B | IMP | TBR | FLEX-290 EEI<20 @ K1 | Spill Over | OEM-HCK | OEM-HCK | ICM | Marketing/Sales |  |  | Development |  | Theoni
102 | 45992 | B | IMP | TBR | ERE3.0 B RATING | Spill Over | OEM-Seitek | OEM-SEITEK | ICM | Marketing/Sales |  |  | Development |  | Theoni
103 | 45940 | A | NM | TBR | Slim CT [R290] | Spill Over | OEM-Seitek | OEM-SEITEK | ICM | Marketing/Sales |  |  | Development |  | Theoni
104 | 45940 | A | NM | TBR | Mini Cube CT [R290] | Spill Over | OEM-Seitek | OEM-SEITEK | ICM | Marketing/Sales |  |  | Development |  | Theoni
105 |  | B | NO | TBR | BEATBOX 3D LOGO PREMIUM SLIM 130 | New | OEM-Seitek | OEM-SEITEK | ICM | Marketing/Sales |  |  | In Que |  | Theoni
106 |  | B | NO | TBR | BEATBOX 3D LOGO FLEX60 | New | OEM-HCK | OEM-HCK | ICM | Marketing/Sales |  |  | In Que |  | Theoni
107 | 45952 | B | NO | TBR | FLEX-130 WITH FDE32 | Spill Over | OEM-Seitek | OEM-SEITEK | ICM | Marketing/Sales |  |  | Development |  | Theoni
108 |  | B | IMP | TBR | FLEX-290 HEINEKEN (EEI<15) | New | OEM-HCK | OEM-HCK | ICM | Marketing/Sales |  |  | In Que |  | Theoni
109 |  | B | IMP | TBR | FLEX-400 HEINEKEN (EEI<15) | New | OEM-HCK | OEM-HCK | ICM | Marketing/Sales |  |  | In Que |  | Theoni
110 |  | B | IMP | TBR | FLEX-130 HEINEKEN (EEI<15) | New | OEM-Seitek | OEM-SEITEK | ICM | Marketing/Sales |  |  | In Que |  | Theoni
111 |  | B | IMP | TBR | MAX-150 HEINEKEN (EEI<15) | New | OEM-Seitek | OEM-SEITEK | ICM | Marketing/Sales |  |  | In Que |  | Theoni
112 | 45976 | A | NM | TBR | TwinReach Monster | New | OEM-Seitek | OEM-SEITEK | ICM | Marketing/Sales |  |  | In Que |  | Theoni
113 |  | B | IMP | TBR | BAR-150 EER B | New | OEM-HCK | OEM-HCK | ICM | Marketing/Sales |  |  | In Que |  | Theoni
114 |  | B | IMP | TBR | BAR-250 EER B Coca Cola | New | OEM-HCK | OEM-HCK | ICM | Marketing/Sales |  |  | In Que |  | Theoni
115 | 45909 | B | CER | TBR | IC2-40 ECO CC Certification | Spill Over | ROM | PD-Romania | ICM | Marketing/Sales |  |  | Development |  | Theoni
116 |  | B | IMP | TBR | Flex-60 EEI<25 | New | OEM-HCK | OEM-HCK | ICM | Marketing/Sales |  |  | In Que |  | Theoni
117 |  | B | IMP | TBR | Flex-60 SZ EEI<25 | New | OEM-HCK | OEM-HCK | ICM | Marketing/Sales |  |  | In Que |  | Theoni
118 |  | A | NO | TBR | Replacement of S-16 | New | OEM-Seitek | OEM-SEITEK | ICM | Marketing/Sales |  |  | In Que |  | Theoni
119 |  | B | NO | TBR | 3D logo for FLEX-130 | New | OEM-Seitek | OEM-SEITEK | ICM | Marketing/Sales |  |  | In Que |  | Theoni
120 |  | B | IMP | TBR | S99 EER Improvement | New | OEM-HCK | OEM-HCK | ICM | Marketing/Sales |  |  | In Que |  | Theoni
121 |  | B | NO | TBR | ERE 3.0 HC @ 60HZ CC Requirements | New | OEM-Seitek | OEM-SEITEK | ICM | Marketing/Sales |  |  | In Que |  | Theoni
122 |  | B | NO | TBR | Flex 65 ECO Ambient light Heineken Germany | New | OEM-HCK | OEM-HCK | ICM | Marketing/Sales |  |  | In Que |  | Theoni
123 |  | B | IMP | TBR | Norcool models Improvements | New | OEM-Seitek | OEM-SEITEK | ICM | Marketing/Sales |  |  | In Que |  | Theoni
124 |  | A | NM | TBR | 35 Lt counter top -Internal or OEM | New | OEM-Seitek |  | ICM | Marketing/Sales |  |  | In Que |  | Theoni
125 |  | A | NM | TBR | 55-60 Lt counter top - Internal or OEM | New | OEM-Seitek |  | ICM | Marketing/Sales |  |  | In Que |  | Theoni
[5 empty] | RPDO hub | PD-Romania
[5 empty] | Count of Project Type | Column Labels
[5 empty] | Row Labels | New | Spill Over | Grand Total
[5 empty] | Central Procurement Group |  | 11 | 11 | 57.89%
[5 empty] | B |  | 10 | 10 | 52.63%
[5 empty] | C |  | 1 | 1 | 5.263%
[5 empty] | Marketing/Sales | 5 | 4 | 9 | 47.37%
[5 empty] | A |  | 1 | 1 | 5.263%
[5 empty] | B | 4 | 1 | 5 | 26.32%
[5 empty] | C | 1 | 2 | 3 | 15.79%
[5 empty] | Grand Total | 5 | 15 | 20
[5 empty] | Count of Plant/OEM | Column Labels
[6 empty] | New |  |  |  |  | New Total | Spill Over | [6 empty] | wk11: Spill Over Total; wk12: Grand Total
[5 empty] | Row Labels | IND | ROM | SAF | OEM-Seitek | OEM-HCK |  | Egypt | IND | INN | Multiplant | ROM | SAF | OEM-Seitek | wk10: OEM-HCK
[5 empty] | Central Procurement Group | [7 empty] | 1 |  | 10 | 11 |  |  | wk11: 22; wk12: 22
[5 empty] | B | [10 empty] | 10 |  |  | wk11: 10; wk12: 10
[5 empty] | C | [7 empty] | 1 |  | 10 | 1 |  |  | wk11: 12; wk12: 12
[5 empty] | Marketing/Sales | 9 | 12 | 8 | 10 | 9 | 48 | 2 | 19 | 3 | 1 | 17 | 1 | 6 | wk10: 1; wk11: 50; wk12: 98
[5 empty] | A | 3 | 3 | 1 | 4 |  | 11 |  |  | 1 |  | 6 |  | 2 | wk11: 9; wk12: 20
[5 empty] | B | 6 | 8 | 2 | 6 | 9 | 31 | 2 | 19 | 2 | 1 | 7 |  | 2 | wk10: 1; wk11: 34; wk12: 65
[5 empty] | C |  | 1 | 5 |  |  | 6 |  |  |  |  | 4 | 1 |  | wk11: 5; wk12: 11
[5 empty] | A-OEM | [12 empty] | 1 | bar: wk11 to wk12
[5 empty] | B-OEM | [12 empty] | 1 | bar: wk11 to wk12
[5 empty] | PD | 1 |  |  |  |  | 1 |  | 3 | [5 empty] | wk11: 3; wk12: 4
[5 empty] | B | 1 |  |  |  |  | 1 |  | 3 | [5 empty] | wk11: 3; wk12: 4
[5 empty] | Grand Total | 10 | 12 | 8 | 10 | 9 | 49 | 2 | 23 | 3 | 11 | 28 | 1 | 6 | wk10: 1; wk11: 75; wk12: 124
[5 empty] | RPDO hub | (Multiple Items)
[5 empty] | Count of Plant/OEM | Column Labels
[6 empty] | New |  | New Total | Spill Over |  | Spill Over Total | Grand Total
[5 empty] | Row Labels | OEM-HCK | OEM-Seitek |  | OEM-HCK | OEM-Seitek
[5 empty] | Marketing/Sales | 9 | 8 | 17 | 1 | 6 | 7 | 24
[5 empty] | A |  | 2 | 2 |  | 2 | 2 | 4
[5 empty] | A-OEM |  |  |  |  | 1 | 1 | 1
[5 empty] | B | 9 | 6 | 15 | 1 | 2 | 3 | 18
[5 empty] | B-OEM |  |  |  |  | 1 | 1 | 1
[5 empty] | Grand Total | 9 | 8 | 17 | 1 | 6 | 7 | 24
Note on AK3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Creo & PLM upgradation training

## 2026-Charter-Delete (hidden)
Count of Customer | Column Labels
Row Labels | IND | INN | Multiplant | SAF | Egypt | Grand Total
Marketing/Sales | 28 | 3 | 1 | 9 | 2 | 43 | 74.14%
A | 3 | 1 |  | 1 |  | 5 | 8.621%
Spill Over |  | 1 |  |  |  | 1 | 1.724%
New | 3 |  |  | 1 |  | 4 | 6.897%
B | 25 | 2 | 1 | 2 | 2 | 32 | 55.17%
Spill Over | 19 | 2 | 1 |  | 2 | 24 | 41.38%
New | 6 |  |  | 2 |  | 8 | 13.79%
C |  |  |  | 6 |  | 6 | 10.34%
Spill Over |  |  |  | 1 |  | 1 | 1.724%
New |  |  |  | 5 |  | 5 | 8.621%
PD | 4 |  |  |  |  | 4 | 6.897%
B | 4 |  |  |  |  | 4 | 6.897%
Spill Over | 3 |  |  |  |  | 3 | 5.172%
New | 1 |  |  |  |  | 1 | 1.724%
Central Procurement Group | 1 |  | 10 |  |  | 11 | 18.97%
C | 1 |  | 10 |  |  | 11 | 18.97%
Spill Over | 1 |  | 10 |  |  | 11 | 18.97%
Grand Total | 33 | 3 | 11 | 9 | 2 | 58
| 56.9% | 5.172% | 18.97% | 15.52% | 3.448%
Count of Plant/OEM | Column Labels
Row Labels | Egypt | IND | INN | Multiplant | SAF | Grand Total
Marketing/Sales | 2 | 28 | 3 | 1 | 9 | 43 | 74.14%
A |  | 3 | 1 |  | 1 | 5 | 8.621%
B | 2 | 25 | 2 | 1 | 2 | 32 | 55.17%
C |  |  |  |  | 6 | 6 | 10.34%
PD |  | 4 |  |  |  | 4 | 6.897%
B |  | 4 |  |  |  | 4 | 6.897%
Central Procurement Group |  | 1 |  | 10 |  | 11 | 18.97%
C |  | 1 |  | 10 |  | 11 | 18.97%
Grand Total | 2 | 33 | 3 | 11 | 9 | 58

## Data Backup-17-11-25 (hidden)
| 2025 | 2026 |  |  |  | A | B | C | Sum | %age | Central R&PD | 6 |  | Central R&PD | 2 | 1.047% | Total projects except Marketing
A | 8 | 5 |  |  | ALL | 4 | 56 | 60 | 120 | 62.83% | Marketing/Sales | 78 |  | Marketing/Sales | 78 | 40.84% | 59.16%
B | 112 | 36 |  |  | CC | 2 | 19 | 6 | 27 | 14.14% | PD | 50 |  | PD | 50 | 26.18%
C | 71 | 17 |  |  | KA | 1 | 22 | 4 | 27 | 14.14% | Procurement | 60 |  | Procurement | 60 | 31.41%
| 191 | 58 |  |  | White | 1 | 15 | 1 | 17 | 8.901% | Service | 3 |  | Service | 1 | 0.5236%
[6 empty] | 8 | 112 | 71 | 191 |  | For graph only |  |  | Total | 191
[6 empty] | 4.188% | 58.64% | 37.17% | Total
|  | 2024 | 2025
| A | 2 | 8
| B | 54 | 112
| C | 15 | 71
40.84%
Category wise Project Update- Development
| Total Projects | Cat 'A' | Cat 'B' | Cat 'C'
Registered | 207 | 9 | 120 | 78
191 |  | 4.712% | 62.83% | 40.84%
Completed by 2025 | 117 | 4 | 61 | 52
%age completion | 57% | 44% | 51% | 67%
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.

## Pivot-Charter-obsolete (hidden)
Charter
Global - Total No. of Projects |  |  |  | Requesting department and Current Status | [8 empty] | 2025-26 Pipeline & Project Status- Category of Projects' | [8 empty] | 2025-26 Pipeline & Project Status- RM Saving Projects' | [7 empty] | 2025-26 Pipeline & Project Status- New Model | [9 empty] | Global Project Category per plant | [8 empty] | Global RPDO resources per project Type | [8 empty] | 2025-26 Project Pipeline → Project current development stage
[23 empty] | RM Saving Project Codes | (Multiple Items) | [6 empty] | Product Type | (Multiple Items)
Project Category | (All) |  |  |  | Count of Requesting Department | Column Labels | [33 empty] | Count of Project Category | Column Labels | [7 empty] | Count of Project Type | Column Labels | [7 empty] | Count of Project Type | Column Labels
[5 empty] | Row Labels | Completed | In progress | Delayed | In Que | Cancelled | On hold | Grand Total |  | Project Type | Cost Saving | Business Continiuty | New Model | Improvement | New Option | Service | TechOps & Certification |  | Count of Component Group- For RM saving Project only | Column Labels | [6 empty] | Count of Project Type | Column Labels | [7 empty] | Row Labels | ROM | IND | SAF | INN | Multiplant | OEM-HCK | OEM-Seitek | Grand Total | Row Labels | R&D-Greece | PD-Romania | PD-India | OEM-HCK | OEM-SEITEK | Grand Total |  |  | Row Labels | ROM | IND | INN | SAF | Multiplant | OEM-HCK | OEM-Seitek | Grand Total
Row Labels | Count of RPDO hub |  |  |  | Marketing/Sales | 6 | 37 | 9 | 54 | 4 | 3 | 113 |  | Count of Plant/OEM | Column Labels | [7 empty] | Row Labels | ROM | IND | INN | SAF | Multiplant | Grand Total |  |  | NM | [5 empty] | NM Total | Grand Total | A | 5 | 4 | 2 | 1 |  | 1 |  | 13 | Antonis | 8 |  |  |  |  | 8 | PDD-A | Marketing Brief | PDD-A |  | 1 | 2 | 1 |  |  |  | 4
R&D-Greece | 16 |  |  |  | PD | 2 | 22 | 2 | 24 | 1 | 1 | 52 |  | Row Labels | CO | BC | NM | IMP | NO | SER | Grand Total | Cost Saving | Completed | 1 | 11 |  |  |  | 12 |  | Row Labels | A+ | A | B | C | A-OEM | B-OEM |  |  | A+ | 4 |  | 1 |  |  |  |  | 5 | Theoni | 6 |  |  | 12 | 14 | 32 | PDD-B | Feasibility Study (Conceptual Design) | PDD-B |  | 2 |  | 1 |  |  |  | 3
PD-Romania | 91 |  |  |  | Central Procurement Group | 9 | 31 |  | 34 |  | 7 | 81 |  | ROM | 62 |  | 16 | 2 | 20 | 3 | 103 | Business Continiuty | Cooling Components |  | 8 |  |  |  | 8 |  | ROM | 4 | 5 | 4 | 3 |  |  | 16 | 16 | A-OEM | [6 empty] | 3 | 3 | Vaggelis | 2 |  |  |  |  | 2 | PDD-E | Design Detailing | PDD-E | 8 | 1 |  | 1 |  |  |  | 10
PD-India | 149 |  |  |  | Quality |  |  | 1 |  |  |  | 1 |  | IND | 49 | 21 | 9 | 14 | 16 |  | 109 | New Model | Electrical Components |  | 1 |  |  |  | 1 |  | IND |  | 4 | 5 |  |  |  | 9 | 9 | B | 56 | 64 | 10 | 7 | 10 |  |  | 147 | Stef |  | 21 |  |  |  | 21 | PDD-F | Proof of Concept | PDD-F | 6 | 3 | 1 | 2 |  |  |  | 12
OEM-HCK | 12 |  |  |  | Service | 1 |  |  | 3 | 1 |  | 5 |  | INN | 4 |  | 2 | 2 |  |  | 8 | Improvement | Plastics |  | 2 |  |  |  | 2 |  | INN |  | 1 | 1 |  |  |  | 2 | 2 | B-OEM | [5 empty] | 12 | 11 | 23 | Catalin |  | 2 |  |  |  | 2 | PDD-H | Certification testings & Complaince | PDD-H | 13 | 11 | 2 |  | 7 |  | 1 | 34
OEM-SEITEK | 14 |  |  |  | (blank) | [8 empty] | SAF | 13 |  | 3 | 5 | 1 |  | 22 | New Option | Steel & Parts | 1 |  |  |  |  | 1 |  | SAF | 1 | 2 |  |  |  |  | 3 | 3 | C | 34 | 41 | 9 |  | 3 |  |  | 87 | Adrian |  | 26 |  |  |  | 26 | PDD-I | TF -1 | PDD-I | 20 | 22 | 1 | 5 | 2 |  |  | 50
Grand Total | 282 |  |  |  | Central R&PD |  |  |  | 2 |  |  | 2 |  | Multiplant | 9 |  |  | 4 |  |  | 13 | Service | In progress | 13 | 28 | 2 | 6 | 7 | 56 |  | OEM-HCK | [5 empty] | 7 | 7 | 7 | (blank) | [8 empty] | Alin |  | 12 |  |  |  | 12 | PDD-J | Pr. Pr | PDD-J | 9 | 29 |  | 2 |  |  |  | 40
[5 empty] | Central Supply Chain |  | 6 |  | 13 |  |  | 19 |  | Grand Total | 137 | 21 | 30 | 27 | 37 | 3 | 255 |  | Cooling Components | 10 | 4 | 2 | 5 |  | 21 |  | OEM-Seitek |  |  |  |  | 3 | 4 | 7 | 7 | Grand Total | 99 | 109 | 22 | 8 | 13 | 13 | 14 | 278 | Lokesh |  |  | 31 |  |  | 31 | PDD-K | TF -2 | PDD-K | 3 | [6 empty] | 3
[5 empty] | Grand Total | 18 | 96 | 12 | 130 | 6 | 11 | 273 | [10 empty] | Electrical Components | 1 | 12 |  | 1 | 7 | 21 |  | Grand Total | 5 | 12 | 10 | 3 | 3 | 11 | 44 | 44 | [9 empty] | Pawan |  |  | 20 |  |  | 20 | PDD-N | Commercialization | PDD-N | 7 |  |  | 4 | 4 |  |  | 15
[23 empty] | Other | 1 | 1 |  |  |  | 2 | [19 empty] | Rishi |  |  | 22 |  |  | 22 | OEM-A | Commercial Brief | OEM-A | [6 empty] | 1 | 1
[23 empty] | Plastics | 1 |  |  |  |  | 1 | [19 empty] | Zakir |  |  | 15 |  |  | 15 | OEM-B | Final Technical Brief & Project Kick Off | OEM-B | [5 empty] | 4 |  | 4
[23 empty] | Steel & Parts |  | 11 |  |  |  | 11 | [19 empty] | Ashwin |  |  | 15 |  |  | 15 | OEM-G | Test results analysis | OEM-G | [5 empty] | 1 | 1 | 2
[23 empty] | In Que | 38 | 9 | 2 | 7 | 2 | 58 | [19 empty] | Nikhil |  |  | 14 |  |  | 14 | OEM-H | Certification testings & Complaince | OEM-H | [5 empty] | 1 | 5 | 6
[23 empty] | Cooling Components | 18 | 2 | 2 |  |  | 22 | [19 empty] | Sailesh |  |  | 2 |  |  | 2 | OEM-J | Pr. Pr | OEM-J | [5 empty] | 2 | 2 | 4
[23 empty] | Door Components & Acc. | 4 | 1 |  |  |  | 5 | [19 empty] | Grand Total | 16 | 61 | 119 | 12 | 14 | 222 | OEM-N | Commercialization | OEM-N | [6 empty] | 1 | 1
[23 empty] | Electrical Components | 14 |  |  | 2 | 2 | 18 | [28 empty] | (blank) | 28 | 3 | [5 empty] | 31
[23 empty] | Other | 2 | 1 |  | 1 |  | 4 | [28 empty] | Not Started | 9 | 37 | 2 | 6 |  | 5 | 3 | 62
[23 empty] | Plastics |  |  |  | 1 |  | 1 | [28 empty] | Grand Total | 103 | 109 | 8 | 22 | 13 | 13 | 14 | 282
[23 empty] | Steel & Parts |  | 5 |  | 3 |  | 8
(blank)
[23 empty] | Cancelled |  | 1 |  |  |  | 1
[23 empty] | Steel & Parts |  | 1 |  |  |  | 1
[23 empty] | Delayed | 2 |  |  |  |  | 2
[23 empty] | Electrical Components | 2 |  |  |  |  | 2 | [37 empty] | PDD-J | PDD-K
[23 empty] | On hold | 8 |  |  |  |  | 8 | [37 empty] | Pr. Pr | TF -2
[23 empty] | Electrical Components | 7 |  |  |  |  | 7
[23 empty] | Steel & Parts | 1 |  |  |  |  | 1
[23 empty] | Grand Total | 62 | 49 | 4 | 13 | 9 | 137
[58 empty] | PDD-A | PDD-B | PDD-C | PDD-D | PDD-E | PDD-F | PDD-G | PDD-H | PDD-I |  |  | PDD-L | PDD-M | PDD-N
[58 empty] | Marketing Brief | Feasibility Study (Conceptual Design) | Business case Approval | Final Technical Brief & Project Kick Off | Design Detailing | Proof of Concept | Online CAPEX approval | Certification testings & Complaince | TF -1 |  |  | Pilot | TF-3 | Commercialization
Draft Project Conversion Factor (A,B & C) project
| Time | %age | Factor
A | 9 | 70.59% | 3
B | 3 | 23.53% | 1
C | 0.75 | 5.882% | 0.25
| 12.75 | 100%
Charter-OPCO
2025-26 Pipeline & Project Status- Category of Projects'

## LTs_IND (hidden)
Project Type ¦ Phase | [11 empty] | A | B | C | D | E | F | G | H | I | J | K
[12 empty] | Sourcing | Sourcing | Sourcing | PDD | Procur. | Procur. | SC | PDD | ENG | PDD | SC
[12 empty] | RFI | SUP_EVAL | SAMPLING | FPAP | SUP_SEL | RFQ | PRE_ORDER | TF | INDUSTR | FIELD_TEST | PO
Type Ib - Int. Spec. Chg. | bar: F; K
Type II - Extension | bar: C to D; F to G; K
Type III - Alt. Sourcing
Type IV - New Sourcing
RM Category | # Prjs | Ib | II | III | IV | PR | SR | PD | PL | kEur | I-Chg | A: Lead Times (wks) per Phase - IND | Total LT | Max Phase
Compressors | 14 |  |  | 1 | 13 |  | 13 | 1 |  | 460.6473 | N | 3 | 2 | 6 | 10 | 1 | 1 |  | 3 | 1 | 16 | 8.5714 | 51.5714 | FIELD_TEST | FPAP and TF timelines are per Compressor per model
Met. Proc. & Comp. | 7 | 3 |  | 4 |  | 5 |  | 2 |  | 88.0778 | Y | 3 | 4 | 8 | 2 | 1 | 1 |  | 1 | 1 | 0 | 1 | 22 | SAMPLING | FPAP and TF timelines are per metal component testing
PSU | 3 |  |  | 1 | 2 |  | 2 | 1 |  | 83.984 | Y/N | 4 | 4 | 7 | 4 | 1 | 1 |  | 2 | 1 | 16 | 12.8571 | 52.8571 | FIELD_TEST | FPAP and TF timelines per PSU
Glass** | 1 |  | 1 |  |  | 1 |  |  |  | 60 | Y | 2 | 4 | 3 | 3 | 1 | 1 |  | 1 | 1 | 0 | 2 | 18 | SUP_EVAL | IPD. EC and Codensation and Glass breakage test (tempered) | if imported due to spacer, then 11 weeks
Steel-GI* | 1 |  |  | 1 |  | 1 |  |  |  | 55 | Y | 3 | 4 | 4 | 4 | 1 | 1 |  | 1 | 1 | 0 | 8.5714 | 27.5714 | PO | 500 hrs SST, SAR by Quality | does not include samples production and delivery for industrialization/pilot production / need to include in the respective Industrialization section
Injection Plastics | 4 | 2 | 1 | 1 |  | 1 |  | 3 |  | 42.7444 | Y | 3 | 4 | 12 | 3 | 1 | 1 |  | 3 | 1 | 0 | 1 | 29 | SAMPLING | PD evaluation time, SAR by Quality
LED | 2 | 1 | 1 |  |  | 1 |  | 1 |  | 38.6 | Y/N | 4 | 4 | 4 | 3 | 1 | 2 |  | 2 | 1 | 4 | 6.4286 | 31.4286 | PO | Alpha testing at plant for 4 weeks
Printing Materials | 3 | 1 |  | 2 |  | 2 |  | 1 |  | 37.3422 | Y | 3 | 2 | 3 | 0 | 1 | 1 |  | 2 | 1 | 0 | 1 | 14 | RFI
Thermostats | 1 |  |  | 1 |  |  |  | 1 |  | 30.7 | Y | 3 | 2 | 3 | 3 | 1 | 1 |  | 2 | 1 | 4 | 12.8571 | 32.8571 | PO | Alpha testing at plant for 4 weeks (Check Cut in / Cut Out)
Magnetic Gaskets | 2 |  |  | 2 |  | 2 |  |  |  | 27.5556 | Y | 3 | 4 | 8 | 8 | 1 | 1 |  | 1 | 1 | 0 | 2.1429 | 29.1429 | SAMPLING | PD evaluation time, SAR by Quality
Locks | 2 |  | 1 | 1 |  | 2 |  |  |  | 19.1889 | Y | 2 | 2 | 3 | 3 | 1 | 1 |  | 1 | 1 | 0 | 2.1429 | 16.1429 | SAMPLING | PD evaluation time, SAR by Quality
Controllers & Access. | 1 |  | 1 |  |  | 1 |  |  |  | 18.57 | N | 2 | 4 | 6 | 0 | 1 | 1 |  | 0 | 1 | 0 | 12.8571 | 27.8571 | PO | 24IND006 - IPS SOB increase to Sirius Solar
Cable Harnesses | 1 |  |  | 1 |  | 1 |  |  |  | 17.6906 | Y | 3 | 4 | 6 | 2 | 1 | 2 |  | 0 | 1 | 0 | 2.1429 | 21.1429 | SAMPLING | SAR by Quality
Block Motors | 1 |  |  |  | 1 |  | 1 |  |  | 16.2 | Y | 3 | 4 | 8 | 4 | 1 | 1 |  | 2 | 1 | 16 | 10.7143 | 50.7143 | FIELD_TEST | PD evaluation time, SAR by Quality
Aluminium Profiles | 1 |  |  | 1 |  | 1 |  |  |  | 16 | Y | 3 | 4 | 7 | 8 | 1 | 1 |  | 0 | 1 | 0 | 4.2857 | 29.2857 | FPAP | Door Opening Test, SAR by Quality
Extrusion Profiles | 2 |  |  | 2 |  | 2 |  |  |  | 12.2222 | Y | 3 | 4 | 8 | 8 | 1 | 1 |  | 0 | 1 | 0 | 1 | 27 | SAMPLING | Door Opening Test, SAR by Quality
WOT | 2 |  |  | 2 |  | 2 |  |  |  | 11.5313 | Y | 5 | 4 | 6 | 2 | 1 | 2 |  | 2 | 1 | 0 | 10 | 33 | PO | PD evaluation time, SAR by Quality
HEX | 1 | 1 |  |  |  | 1 |  |  |  | 6.0667 | Y | 5 | 4 | 6 | 2 | 1 | 2 |  | 2 | 1 | 0 | 2.1429 | 25.1429 | SAMPLING | PD evaluation time, SAR by Quality
| 49 | 8 | 5 | 20 | 16 | 23 | 16 | 10 | 0 | 1042.1209
Procurement
Sourcing
PDD
Supply Chain
Production
Engineering
Quality

## LTs_SAF (hidden)
Project Type ¦ Phase | [11 empty] | A | B | C | D | E | F | G | H | I | J | K
[12 empty] | Sourcing | Sourcing | Sourcing | PDD | Procur. | Procur. | SC | PDD | ENG | PDD | SC
[12 empty] | RFI | SUP_EVAL | SAMPLING | FPAP | SUP_SEL | RFQ | PRE_ORDER | TF | INDUSTR | FIELD_TEST | PO
Type Ib - Int. Spec. Chg. | bar: F; K
Type II - Extension | bar: C to D; F to G; K
Type III - Alt. Sourcing
Type IV - New Sourcing
RM Category | # Prjs | Ib | II | III | IV | PR | SR | PD | PL | kEur | I-Chg | A: Lead Times (wks) per Phase - SAF | Total LT | Max Phase
Compressors | 4 |  |  | 2 | 2 |  | 1 | 3 |  | 260.7079 | N | 3 | 2 | 8 | 10 | 1 | 1 |  | 3 | 1 | 16 | 20 | 65 | PO | FPAP and TF timelines are per Compressor per model
Met. Proc. & Comp. | 10 | 8 |  | 2 |  | 5 |  | 4 | 1 | 142.9307 | Y | 3 | 4 | 8 | 2 | 1 | 1 |  | 1 | 1 | 0 | 1.5 | 22.5 | SAMPLING | FPAP and TF timelines are per metal component testing
Copper Tubes | 5 | 5 | [5 empty] | 5 |  | 79.811 | Y | 2 | 4 | 6 | 2 | 1 | 1 |  | 1 | 1 | 0 | 20 | 38 | PO | Evaluation by Engineering, SAR by Quality
Steel-PPGI | 2 | 1 |  | 1 |  | 1 |  | 1 |  | 75.63 | Y | 3 | 4 | 4 | 0 | 1 | 1 |  | 0 | 1 | 0 | 1.5 | 15.5 | SUP_EVAL | 24SAF015 - Sky Steel SOB Increase | does not include samples production and delivery for industrialization/pilot production / need to include in the respective Industrialization section
Sh. Pole Mot. & Blad. | 2 |  |  | 2 |  |  |  | 2 |  | 42.25 | Y | 2 | 4 | 6 | 0 | 1 | 1 |  | 2 | 1 | 0 | 20 | 37 | PO | Alpha testing already done by PD
Fastening Materials | 1 |  |  | 1 |  | 1 |  |  |  | 24.65 | Y | 4 | 4 | 3 | 0 | 1 | 2 |  | 0 | 1 | 0 | 1.5 | 16.5 | RFI
Other Materials | 2 | 2 |  |  |  | 1 |  | 1 |  | 22.697 | Y | 4 | 4 | 3 | 1 | 1 | 2 |  | 1 | 1 | 0 | 1.5 | 18.5 | RFI | Project cancelled after CCBSA Oct meeting
Wooden Pallets | 1 | 1 | [5 empty] | 1 |  | 17.25 | Y | 3 | 4 | 3 | 2 | 1 | 1 |  | 2 | 1 | 0 | 1.5 | 18.5 | SUP_EVAL | Evaluation by Engineering, SAR by Quality
Steel-GI | 1 |  |  | 1 |  | 1 |  |  |  | 13.5 | Y | 3 | 4 | 4 | 4 | 1 | 1 |  | 1 | 1 | 0 | 1.5 | 20.5 | SUP_EVAL | 500 hrs SST, SAR by Quality | does not include samples production and delivery for industrialization/pilot production / need to include in the respective Industrialization section
LED | 6 |  |  | 3 | 3 |  | 3 | 3 |  | 13.4166 | Y/N | 4 | 4 | 10 | 0 | 1 | 2 |  | 1 | 1 | 0 | 21 | 44 | PO
PSU | 3 |  |  | 3 |  |  |  | 3 |  | 13.11 | Y/N | 4 | 4 | 6 | 4 | 1 | 1 |  | 2 | 1 | 16 | 23 | 62 | PO | FPAP and TF timelines per PSU
Cable Harnesses | 3 | 3 | [5 empty] | 3 |  | 12.485 | Y | 3 | 4 | 6 | 2 | 1 | 2 |  | 1 | 1 | 0 | 1.5 | 21.5 | SAMPLING | Evaluation by Engineering, SAR by Quality
Injection Plastics | 2 |  |  | 2 |  | 1 |  | 1 |  | 11.6667 | Y | 3 | 4 | 14 | 2 | 1 | 1 |  | 3 | 1 | 0 | 4.5 | 33.5 | SAMPLING | GWT by PD IND, SAR by Quality
Labels & Manuals | 1 |  |  | 1 |  | 1 |  |  |  | 9.1667 | Y | 3 | 2 | 3 | 1 | 1 | 1 |  | 0 | 1 | 0 | 1.5 | 13.5 | RFI | Approval by Sales/Marketing
HEX | 2 |  |  | 1 | 1 | 1 |  | 1 |  | 8.157 | Y | 5 | 4 | 6 | 2 | 1 | 2 |  | 2 | 1 | 0 | 20 | 43 | PO | PD evaluation time, SAR by Quality
Thermostats | 1 |  |  | 1 |  |  |  | 1 |  | 3.738 | Y | 3 | 2 | 5 | 3 | 1 | 1 |  | 2 | 1 | 4 | 20 | 42 | PO | Alpha testing at plant for 4 weeks (Check Cut in / Cut Out)
Shelves | 1 | 1 | [5 empty] | 1 |  | 1.4 | Y | 2 | 4 | 6 | 1 | 1 | 1 |  | 1 | 1 | 0 | 23 | 40 | PO | SAR by Plant
WOT | 1 |  |  |  | 1 |  |  | 1 |  | 1 | Y | 5 | 4 | 6 | 2 | 1 | 2 |  | 2 | 1 | 0 | 23 | 46 | PO | PD evaluation time, SAR by Quality
| 48 | 21 | 0 | 20 | 7 | 12 | 4 | 31 | 1 | 753.5665
Procurement
Sourcing
PDD
Supply Chain
Production
Engineering
Quality

## LTs_INN (hidden)
Project Type ¦ Phase | [11 empty] | A | B | C | D | E | F | G | H | I | J | K
[12 empty] | Sourcing | Sourcing | Sourcing | PDD | Procur. | Procur. | SC | PDD | ENG | PDD | SC
[12 empty] | RFI | SUP_EVAL | SAMPLING | FPAP | SUP_SEL | RFQ | PRE_ORDER | TF | INDUSTR | FIELD_TEST | PO
Type Ib - Int. Spec. Chg. | bar: F; K
Type II - Extension | bar: C to D; F to G; K
Type III - Alt. Sourcing
Type IV - New Sourcing
RM Category | # Prjs | Ib | II | III | IV | PR | SR | PD | PL | kEur | I-Chg | A: Lead Times (wks) per Phase - INN | Total LT | Max Phase
Compressors | 2 | 2 | [5 empty] | 2 |  | 79.1073 | N | 3 | 2 | 6 | 10 | 1 | 1 |  | 3 | 1 | 16 | 8 | 51 | FIELD_TEST | FPAP and TF timelines are per Compressor per model | could be as high as 11 for specific PCDs
Protector - Stabilizer | 2 | 1 | 1 |  |  |  |  | 2 |  | 63.5976 | Y | 6 | 4 | 8 | 3 | 1 | 2 |  | 2 | 1 | 16 | 8 | 51 | FIELD_TEST | Testing by PD, SAR by Quality | could be as high as 12 for specific PCDs
Silk Screened Parts | 3 |  | 1 | 1 | 1 |  | 1 | 2 |  | 39.3679 | Y | 3 | 2 | 3 | 1 | 1 | 1 |  | 2 | 1 | 0 | 2 | 16 | RFI | Marketing / Sales approval
Steel-GI* | 5 | 5 | [5 empty] | 5 |  | 35.7725 | Y | 3 | 4 | 4 | 1 | 1 | 1 |  | 2 | 1 | 0 | 14 | 31 | PO | SAR by Quality | does not include samples production and delivery for industrialization/pilot production / need to include in the respective Industrialization section
Steel-PPGI* | 1 |  |  | 1 |  |  |  |  | 1 | 21 | Y | 3 | 4 | 4 | 1 | 1 | 1 |  | 0 | 1 | 0 | 12 | 27 | PO | SAR by Quality | does not include samples production and delivery for industrialization/pilot production / need to include in the respective Industrialization section
PSU | 2 | 1 |  | 1 |  | 1 |  | 1 |  | 19.1495 | Y/N | 4 | 4 | 6 | 4 | 1 | 1 |  | 2 | 1 | 16 | 5 | 44 | FIELD_TEST | FPAP and TF timelines per PSU
Plastic bags & Str. Film | 1 |  |  | 1 |  |  |  |  | 1 | 12.2 | Y | 3 | 2 | 4 | 1 | 1 | 1 |  | 1 | 1 | 0 | 5 | 19 | PO | SAR by Quality
LED | 2 |  |  | 1 | 1 | 1 |  |  | 1 | 11.9953 | Y/N | 4 | 4 | 10 | 3 | 1 | 2 |  | 2 | 1 | 4 | 5 | 36 | SAMPLING | Alpha testing at plant for 4 weeks
Extrusion pl. Profiles** | 2 | 1 | 1 | [5 empty] | 2 | 8.9545 | Y | 3 | 4 | 8 | 1 | 1 | 1 |  | 0 | 1 | 0 | 3 | 22 | SAMPLING | SAR by Quality | 8 if imported
Cable Harnesses | 3 | 3 | [6 empty] | 3 | 6.8415 | Y | 3 | 4 | 6 | 2 | 1 | 2 |  | 0 | 1 | 0 | 3 | 22 | SAMPLING | SAR by Quality
Assembled Door | 1 | 1 | [6 empty] | 1 | 4.6457 | Y | 4 | 4 | 10 | 8 | 1 | 2 |  | 0 | 1 | 0 | 8 | 38 | SAMPLING | Door Opening Test, SAR by Quality
Fastening Materials | 2 | 2 | [6 empty] | 2 | 3.3812 | Y | 4 | 4 | 3 | 0 | 1 | 2 |  | 0 | 1 | 0 | 4 | 19 | RFI | SAR by Quality
Other Materials | 3 | 3 | [6 empty] | 3 | 3.3528 | Y | 4 | 4 | 3 |  | 1 | 2 |  |  | 1 |  | 3 | 18 | RFI | RM saving project no clear
Magnetic Gaskets | 1 |  |  | 1 |  | 1 |  |  |  | 1.8907 | Y | 3 | 4 | 8 | 8 | 1 | 1 |  | 1 | 1 | 0 | 3 | 30 | SAMPLING | PD evaluation time, SAR by Quality
Controllers & Access. | 2 | 1 | 1 |  |  |  |  | 1 | 1 | 1.3736 | N | 2 | 4 | 6 | 3 | 1 | 1 |  | 2 | 1 | 0 | 6 | 26 | SAMPLING | Alpha testing at plant for 4 weeks
Printing Materials | 1 |  | 1 | [5 empty] | 1 | 0.59681 | Y | 3 | 2 | 3 | 0 | 1 | 1 |  | 0 | 1 | 0 | 3 | 14 | RFI | SAR by Quality
Electrical Components | 1 | 1 | [5 empty] | 1 |  | 0.5426 | Y | 4 | 4 | 8 | 1 | 1 | 2 |  | 1 | 1 | 0 | 8 | 30 | SAMPLING | SAR by Quality
Labels & Manuals | 2 | 2 | [6 empty] | 2 | 0.086413 | Y | 3 | 2 | 3 | 1 | 1 | 1 |  | 2 | 1 | 0 | 2 | 16 | RFI | SAR by Quality
| 36 | 23 | 5 | 6 | 2 | 3 | 1 | 14 | 18 | 313.856
Procurement
Sourcing
PDD
Supply Chain
Production
Engineering
Quality

## Interchangeable (hidden)
Categories | Interchangeable? Y, N, Y/N
Al. Sheets | Y
Aluminium Profiles | Y
Assembled Door | Y
Asset Tags | Y
Back Grids | Y
Ballast | Y
Block Motors | Y/N
Brazing materials | Y
Cable Harnesses | Y
Carton box | Y
Compressor Accessories | N
Compressors | N
Copper Components | Y | *corrected
Copper Tubes | Y
Cross Flow Motors | Y/N
EPS | Y
Electrical Components | Y/N
Electronic Controllers & Acces | N
Electronic Motors | Y/N
Extrusion pl. Profiles | Y
Fastening Materials | Y
Fluorescent Tubes | Y
Glass | Y
HEX | Y
Injection Plastics | Y
LED | Y/N
Labels & Manuals | Y
Locks | Y
Magnetic Gaskets | Y
Metal Processing & Components | Y
Night Blinds | Y
Other Materials | Y
PSU | Y/N
Plastic Sheets | Y
Plastic bags & Stretch Film | Y
Polyurethane Materials | Y
Powders | Y
Power Cables | Y
Printing Materials | Y
Refrigerants | Y
Shaded Pole Motors & Blades | Y/N
Shelves | Y
Silicones | Y
Silk Screened Parts | Y
Steel-GI | Y
Steel-PPGI | Y
Tapes&Other Packaging Material | Y
Thermostats | Y
WOT | Y
Wooden Pallets | Y
Protector - Stabilizer | Y
Thermoformed Parts | Y
HONEYCOMB | Y

## IND_MoM (hidden)
Project Code | Project Name | What | Who | When
ALL | ALL | Sachin & Amit to review each and every project to determine their viability as well as the implementation date. Amit will then realign the "within" volumes accordingly | Sachin/Amit | 2024-11-25
ALL | ALL | The current "within" the year volumes when compared to the annualized volumes in relation to the respective implementation dates, do not seem to be correct. Amit to recalculate the annualized volumes, the within volumes based on the implementation dates and the savings per UoM for each and every project. | Amit | 2024-11-25
24IND005 | FAN casing from metal to plastic | Given the required investments in moulds, amortization over 2 years needs to be taken into account in the calculation of each of the savings projects. | Amit | 2024-11-25
25IND010 | Plastic Fan casing Inclusion of Plastic Fan Casing in S-40/S-45/S-450
25IND011 | Plastic Moulding parts : Alternate Supplier Development EIC & Geeta/Everfine -> Under evaluation
25IND015 | Gasket & Extrusion : In-House Development Ajay Poly -> Sudarshan (In-house) | Implementation date and SOB need to be confirmed with R&PD. Savings calculation needs to be reviewed and updated | Sachin/Amit | 2024-11-25

## INN_MoM (hidden)
Project Code | Project Name | What | Who | When
24INN001 | Localization PCM from Import China to Local | check implementation and saving refer to update trial pilot production readiness | INN Team | Nov 20th
24INN002 | Localization Plastic Stretch Hood from Import Malaysia to Local | re-check implementation date & respective savings | INN Team | Nov 20th
24INN009 | Change Outer cabin Thickness 0.45 to 0.4 mm E47 & SLP400 | re-check implementation date & respective savings | INN Team | Nov 20th
24INN024 | Change P/S type from I Series to L series | in the title, change "i-series" to "i-hybrid series" | INN Team | Nov 20th
25INN004 | Change brand from PSU Meanwell to Tauras 12V,15V,20V,30V | project hold: waiting confirmation from PD (PD evaluation) | INN Team | INN Team to provide timing by Nov 22nd on when 2KV safety data will be available
25INN006 | Change spec digital thermo 12V to 24 PVR CONTROL | not in "electronic controllers & accessories" - change RM category & Component Group | INN Team | Nov 20th
25INN007 | Change compressor WANBAO FTA55L to FTK55X for E47/FV280/SLP400 | (a) Revise project name to : Change compressor WANBAO FTA55L to FKK35. (b) Effective date and saving per unit waiting confirmation PD (Manoj & Sachin). | (a) INN Team (b) Manoj / Sachin | (a) Nov 20th (b) TBC by Nov 22nd
25INN008 | Change compressor Huayi NUY80RAA to doper L76WU1 for FV650/SLP650 | effective date implementation waiting confirmation from PD | Manoj / Sachin | TBC by Nov 22nd
25INN009 | Change P/S type from I Series to L series | Revise project name to : Change P/S type from I Series hybrid to L series. Need to recalculate the saving amount to avoid double counting. | INN Team | Nov 20th
25INN010 | Change all cable dia. 1 mm to 0.75 mm (except grounding cable) | Saving calculation to exclude FV1200 model. Reinstate the deducted volume once approved. | INN Team | Nov 20th
25INN012 | Change thickness front grid FV1200 from 0.6mm to 0.45mm | need to do trial and evaluation by TS and PD | Sachin | TBC - Sachin to provide the time by Nov 20th
25INN013 | Change door Glass to Plastic door complete | need to do trial and evaluation by TS and PD | (a) INN Team (b) Manoj / Sachin | (a) confirm design and door availability (b) upon receipt of above, confirm next actions and dates
25INN017 | Change Outer cabin Thickness 0.45 to 0.4 mm FV650, FV1000 FV1200 | re-check implementation date & respective savings | INN Team | Nov 20th
25INN018 | Change shelves model FV1200 from Shelves FV1200 CR to FV650 CR | project drop – need to do lab test | INN Team | Nov 20th

## ROM_MoM (hidden)
Project Code | Project Name | What | Who | When
24ROM005 | Reduction Thickness Copper Tubes | recheck savings calculations | Marian / Andreea | 2024-11-28
24ROM008 | Tauras PSU vs Alder PSU | recheck savings calculations recheck either implementation date or within | Marian / Andreea | 2024-11-28
24ROM012 | ESTO alternative supplier | recheck either implementation date or within | Andreea | 2024-11-28
25ROM007 | Change inner glass pane from tempered to floating for IC2 doors | recheck either implementation date or within | Andreea | 2024-11-28
25ROM009 | Eliminate RCCB tap and FFXY cover | recheck either implementation date or within | Andreea | 2024-11-28
25ROM010 | Integrate metalic fan grid cover into service lid | to be compared against Vangelis cheaper option and account for investment amortization recheck either implementation date or within | Marian / Andreea | 2024-11-28

## SAF_MoM (hidden)
Project Code | Project Name | What | Who | When
24SAF001 | Compressor NUS70NA-->Donper LZ76WU1 | (a) expect feedback from sales - keep SAF reported volumes (b) expect feedback from Manoj re testing/implementation date (c) delete duplicate (SAF/SRC) | (a) Quinton (b) Manoj (c) Thanassis | Nov 22nd
24SAF002 | Motor ECM7112--> NEC4810 Saiwei | (a) delete duplicates (SAF/SRC) (b) Andreas K. with Andreas D. to redo the component savings calculations | (a) Thanassis (b) Andreas K./ Andreas D. | Nov 22nd
24SAF003 | Motor ECM7120--> NEC6115 Saiwei
24SAF004 | 1/4" Copper tube thickness reduction from 0.76 to 0.65mm | Expedite for 1st quarter. By when can we have the rollers? Beware of the order sequence of the existing thickness. Check sub-zero volumes. Duplicate with 25SAF002 which is removed. | SAF Team | Nov 22nd
24SAF008 | Compressor NUY120NA-->Donper KK480WU1 | (a) Andreas K. with Andreas D. to redo the component savings calculations (b) expect feedback from Manoj re testing/implementation date | (a) Andreas K./ Andreas D. (b) Manoj | (a) Nov 21st (b) Nov 22nd
24SAF016 | HV71 R290 -->A rating Cost Saving - HV71 R290 / moving to A-rating | Proceed with cost breakdown per major RM category | SAF Team | Nov 22nd
24SAF043 | Adler 20W--> Tauras 20W - FV1000 SZ | Redo & confirm saving calculations | SAF Team | Nov 22nd
25SAF003 | Localization for Evaporators | Decide on project viability due to higher cost received | Quinton/ Oscar/ Thanassis | Nov 22nd
25SAF004 | Localization for Drip Tray | Redo saving calculations | SAF Team | Nov 22nd
25SAF005 | Plastic Evap Fan Grill Localization | Redo saving calculations | SAF Team | Nov 22nd
25SAF006 | Non CCBSA Artwork Supplier | Redo volumes & saving calculations | SAF Team | Nov 22nd
25SAF007 | Alternate supplier for Metal Processing & Components in S.A | Share calculations with Thanassis | SAF Team | Nov 21st
25SAF008 | Revisit local shelf clip option | Redo & confirm saving calculations | SAF Team | Nov 22nd
25SAF009 | Sourcing with another local supplier for better pricing - Trident | (a) Share calculations with Thanassis (b) Share all contacted suppliers so far | (a) SAF Team (b) Oscar | Nov 21st
25SRC032 | Fastenings for S.Africa from China | Discuss calculations | Vangelis | Nov 25th
25SRC035 | LED Conrun as alternative to Refond 1200mm | Change Refond to Royalux, redo the calculations and rethink of the implementation dates | Andreas D. | Nov 22nd
25SRC036 | LED Conrun as alternative to Refond 1400mm
25SRC037 | LED Conrun as alternative to Refond 800mm
ALL | ALL | Review Project Type Classification by utilizing the respective questionnaire in the tab "Lists & Explanation". If any answer to any of the questions is "Yes", then the component is considered as "New". | Quentin | Nov 22nd
ALL | ALL | Breakdown high savings projects to their main RM categories | SAF Team | Nov 22nd
ALL | ALL | Indicate all cooler models affected by each project | SAF Team | Nov 22nd

## 14 Vs. 12b (hidden)
| 2024 Spillover | 2025 Within | 2025 Spillover | Total
v12B | 804.755 | 3902.7125 | 1407.7855 | 6115.253
v14 | #REF! | #REF! | #REF! | #REF!
Δ | #REF! | #REF! | #REF! | #REF!